COMHAIRLE CONTAE ÁTHA CLIATH THEAS  
SOUTH DUBLIN COUNTY COUNCIL



MEETING OF RATHFARNHAM/TEMPLEOGUE/FIRHOUSE/BOHERNABREENA AREA COMMITTEE

12th October 2021

HEADED ITEM NO.13

Q3 2021 Housing Supply Programme Quarterly Report

|  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | **Capital Housing Delivered 2020** | | | | | | | | | |
| **Local Authority Build (Including PPP)** | | **AHB Build** | **Part V** | **Total Build** | **LA Acquisition** | **AHB Acquisition** | **Total Acquisitions** | **Total Leasing** | **Voids** | **Grand Total** |
| **109** | | **156** | **105** | **370** | **12** | **21** | **33** | **123** | **10** | **536** |

|  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| **Housing Projected Delivery 2021** | | | | | | | | | | | |
| **LA Build** | **AHB Build** | **Part V** | **Total Build** | **LA Acquisitions** | **AHB Acquisitions** | | **Total Acquisitions** | **Total Leasing** | | **Total 2021 Projected Delivery** | |
| **2** | **146** | **97** | **245** | **13** | **17** | | **30** | **150** | | **425\*** | |
| **Department of Housing Build Target for 2021** | | | **408** |  | | **Department of Housing Leasing Target for 2021** | | | **190** | | **598** |

\* 2021 pipeline revised due to impact on programme of delivery during Level 5 restrictions.

|  |  |  |  |  |
| --- | --- | --- | --- | --- |
| **Housing Build Pipeline for 2021**  **Rathfarnham – Templeogue – Firhouse - Bohernabreena Area** | | | | |
|  | **LA Build** | **AHB Build** | **Part V** | **Total** |
| Rathfarnham-Templeogue | 0 | 11 | 1 | 12 |
| Firhouse- Bohernabreena | 0 | 0 | 9 | 9 |
| **Grand Total** | **0** | **11** | **10** | **21** |

|  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | **Capital Housing Delivered 2021 to end Sept 2021** | | | | | | | | |
| **Local Electoral Area** | **Local Authority Build** | **AHB Build** | **Part V** | ***Total Build*** | **LA Acquisition** | **AHB Acquisition** | ***Total Acquisitions*** | **Total Leasing** | **Grand Total** |
| Rathfarnham- Templeogue | 0 | 11 | 1 | **12** | 0 | 0 | 0 | **8** | **20** |
| Firhouse- Bohernabreena | 0 | 0 | 9 | **9** | 1 | 0 | **1** | **3** | **13** |
| **Grand Total** | **0** | **11** | **10** | **21** | **1** | **1** | **1** | **11** | **33** |

|  |  |  |  |  |
| --- | --- | --- | --- | --- |
| **Construction Programme 2021** | | | | |
| **Projects with Part 8 Planning Approval** | | | | |
| **Local Electoral Area** | **Project Name** | **Part 8 Approved Date** | **No. of Units Approved @ Part 8** | **Current Status** |
| Firhouse/ Bohernabreena | Homeville | 10/09/2018 | 16 | Site Start Nov 2020. Contractor has reported delays in provision of materials which may impact programme for delivery. Projected completion Q2 2022. |
| Rathfarnham/ Templeogue | Templeogue Village | 01/10/2018 | 11 | Budget approved in July 2021, and contractor appointed August 2021 for design build project. Contractor to mobile on site in Q4 2021 with projected delivery Q3 2022. |
|  |  |  | **27** |  |

|  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| **Proposed Part 8’s** | | | | | | |
| **Scheme Location** | | **Local Electoral Area** | | **Proposed no. of Units** | | **Status** |
| Pearse Brothers Park, Rathfarnham, Dublin 16 | | Firhouse/  Bohernabreena | | 10 | | Proposed Older Persons specific housing noted at ACM in November 2020. Part 8 proposed for consideration of members at October 2021 Council meeting. |
| **Total** | |  | | **10** | |  |
| **Part V Delivery Programme for 2021** | | | | | | | |
| **Scheme Name** | **Firhouse/ Bohernabreena** | | **Rathfarnham/ Templeogue** | | **Status of Part V Agreement** | | |
| Dodderbrook, Ballycullen | 9 | |  | | Part V units delivered Q1 2021. | | |
| Willowview, Ballyboden Road, Rathfarnham. |  | | **1** | | Scheme of 12 units acquired by Clúid Housing in June 2021. | | |
| **Grand Total** | **23** | | **1** | |  | | |

|  |  |  |  |
| --- | --- | --- | --- |
| **Part V Agreements in Place** | | | |
| **Scheme Name** | **Firhouse/ Bohernabreena** | **Rathfarnham/ Templeogue** | **Status of Part V Agreement** |
| Scholarstown Woods, Rathfarnham | 14 |  | Part V agreement in place and 14 units due for delivery Q1 2022- delay due to Level 5 restrictions on construction. |
| **Grand Total** | 14 | **0** |  |