COMHAIRLE CONTAE ÁTHA CLIATH THEAS
SOUTH DUBLIN COUNTY COUNCIL

MEETING OF RATHFARNHAM/TEMPLEOGUE/FIRHOUSE/BOHERNABREENA AREA COMMITTEE

12th October 2021

HEADED ITEM NO.13

Q3 2021 Housing Supply Programme Quarterly Report

|  | Capital Housing Delivered 2020 |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Local Authority Build (Including PPP) |  | AHB Build | Part V | Total Build | LA Acquisition | AHB Acquisition | Total Acquisitions | Total Leasing | Voids | Grand Total |
| 109 |  | 156 | 105 | 370 | 12 | 21 | 33 | 123 | 10 | 536 |

| Housing Projected Delivery 2021 |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| LA Build | AHB Build | Part V | Total Build | LA Acquisitions | AHB Acquisitions |  | Total Acquisitions | Total Leasing |  | Total 2021 Projected Delivery |  |
| 2 | 146 | 97 | 245 | 13 | 17 |  | 30 | 150 |  | 425* |  |
| Department of Housing Build Target for 2021 |  |  | 408 |  |  | Department of Housing Leasing Target for 2021 |  |  | 190 |  | 598 |

* 2021 pipeline revised due to impact on programme of delivery during Level 5 restrictions.

| Housing Build Pipeline for 2021 Rathfarnham – Templeogue – Firhouse - Bohernabreena Area |  |  |  |  |
| --- | --- | --- | --- | --- |
|  | LA Build | AHB Build | Part V | Total |
| Rathfarnham-Templeogue | 0 | 11 | 1 | 12 |
| Firhouse- Bohernabreena | 0 | 0 | 9 | 9 |
| Grand Total | 0 | 11 | 10 | 21 |

|  | Capital Housing Delivered 2021 to end Sept 2021 |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Local Electoral Area | Local Authority Build | AHB Build | Part V | Total Build | LA Acquisition | AHB Acquisition | Total Acquisitions | Total Leasing | Grand Total |
| Rathfarnham- Templeogue | 0 | 11 | 1 | 12 | 0 | 0 | 0 | 8 | 20 |
| Firhouse- Bohernabreena | 0 | 0 | 9 | 9 | 1 | 0 | 1 | 3 | 13 |
| Grand Total | 0 | 11 | 10 | 21 | 1 | 1 | 1 | 11 | 33 |

| Construction Programme 2021 |  |  |  |  |
| --- | --- | --- | --- | --- |
| Projects with Part 8 Planning Approval |  |  |  |  |
| Local Electoral Area | Project Name | Part 8 Approved Date | No. of Units Approved @ Part 8 | Current Status |
| Firhouse/ Bohernabreena | Homeville | 10/09/2018 | 16 | Site Start Nov 2020. Contractor has reported delays in provision of materials which may impact programme for delivery. Projected completion Q2 2022. |
| Rathfarnham/ Templeogue | Templeogue Village | 01/10/2018 | 11 | Budget approved in July 2021, and contractor appointed August 2021 for design build project. Contractor to mobile on site in Q4 2021 with projected delivery Q3 2022. |
|  |  |  | 27 |  |

| Proposed Part 8’s |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Scheme Location |  | Local Electoral Area |  | Proposed no. of Units |  | Status |
| Pearse Brothers Park, Rathfarnham, Dublin 16 |  | Firhouse/ Bohernabreena |  | 10 |  | Proposed Older Persons specific housing noted at ACM in November 2020. Part 8 proposed for consideration of members at October 2021 Council meeting. |
| Total |  |  |  | 10 |  |  |
| Part V Delivery Programme for 2021 |  |  |  |  |  |  |  |
| Scheme Name | Firhouse/ Bohernabreena |  | Rathfarnham/ Templeogue |  | Status of Part V Agreement |  |  |
| Dodderbrook, Ballycullen | 9 |  |  |  | Part V units delivered Q1 2021. |  |  |
| Willowview, Ballyboden Road, Rathfarnham. |  |  | 1 |  | Scheme of 12 units acquired by Clúid Housing in June 2021. |  |  |
| Grand Total | 23 |  | 1 |  |  |  |  |

| Part V Agreements in Place |  |  |  |
| --- | --- | --- | --- |
| Scheme Name | Firhouse/ Bohernabreena | Rathfarnham/ Templeogue | Status of Part V Agreement |
| Scholarstown Woods, Rathfarnham | 14 |  | Part V agreement in place and 14 units due for delivery Q1 2022- delay due to Level 5 restrictions on construction. |
| Grand Total | 14 | 0 |  |