COMHAIRLE CONTAE ÁTHA CLIATH THEAS
SOUTH DUBLIN COUNTY COUNCIL

MEETING OF RATHFARNHAM/TEMPLEOGUE/FIRHOUSE/BOHERNABREENA AREA COMMITTEE

11th January 2022

HEADED ITEM NO.16

| CAPTIAL HOUSING DELIVERY 2020-2022 |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | BUILD |  |  |  |  |  |  | LEASING |  | ACQUISTIONS |  |  |
| Year | LA New Build | AHB New Build | Part V New Build | PPP Build | JV Build | Total New Build | DHLGH Build Target | Leasing Total | DHLGH Leasing Targets | LA | AHB | Total |
| 2020 | 0 | 156 | 108 | 109 | 0 | 373 | 467 | 119 | 120 | 13 | 20 | 33 |
| 2021 | 2 | 137 | 108 | 0 | 0 | 245 | 245* | 159 | 150* | 2 | 1 | 3 |
|  | Original DHLGH Target |  |  |  |  |  | 408 |  | 190 |  |  |  |

Q1 2022 Housing Supply Programme Quarterly Report

* 2021 pipeline revised due to impact on programme of delivery during Level 5 restrictions.

| HOUSING FOR ALL TARGETS 2022 |  |  |  |
| --- | --- | --- | --- |
| Year | Build | Leasing | Total SDCC Target 2022 |
| 2022 | 400 | 40 | 440 |

|  | Capital Housing Delivery Comparison Years 2020 and 2021 RATHFARNHAM/TEMPLEOGUE and FIRHOUSE/BOHERNABREENA AREAS |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Area |  | LA New Build | AHB New Build | Part V New Build | Total New Build | LEASING TOTAL | Acquisitions Total | Total PA Delivered Units per Area |
| Rathfarnham-Templeogue 2020 |  | 0 | 0 | 0 | 0 | 26 | 4 | 30 |
| Rathfarnham-Templeogue 2021 |  | 0 | 11 | 10 | 21 | 8 | 0 | 29 |
| Firhouse- Bohernabreena 2020 |  | 0 | 0 | 0 | 0 | 1 | 2 | 3 |
| Firhouse- Bohernabreena 2021 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |

| Construction Programme 2022 |  |  |  |  |
| --- | --- | --- | --- | --- |
| Projects with Part 8 Planning Approval |  |  |  |  |
| Local Electoral Area | Project Name | Part 8 Approved Date | No. of Units Approved @ Part 8 | Current Status |
| Firhouse/ Bohernabreena | Homeville | 10/09/2018 | 16 | Under construction. Due for completion Q3 2022 |
| Firhouse/ Bohernabreena | Pearse Brothers Park, Rathfarnham, Dublin 16 | 11/10/2021 | 10 | Part 8 approved October 2021. Project to proceed to detailed design Q1 2022. Expected to be completed 2023. |
| Rathfarnham/ Templeogue | Templeogue Village | 01/10/2018 | 11 | Contractor appointed & commencing on site January 2022. |
|  |  |  | 37 |  |

| Part V Delivery Programme for 2022 |  |  |  |
| --- | --- | --- | --- |
| Scheme Name | Firhouse/ Bohernabreena | Rathfarnham/ Templeogue | Status of Part V Agreement |
| Scholarstown Woods, Rathfarnham | 14 | 0 | Part V agreement in place and 14 units due for delivery Q1 2022- delay due to Level 5 restrictions on construction. |
| Grand Total | 14 | 0 |  |

As of Year to Date, there are no additional Part V Agreements within this LEA to report on.