COMHAIRLE CONTAE ÁTHA CLIATH THEAS
SOUTH DUBLIN COUNTY COUNCIL

Clondalkin Area Committee Meeting

19th January 2022

HEADED ITEM NO.19

Q1 2022 Housing Supply Programme Quarterly Report

| CAPTIAL HOUSING DELIVERY 2020-2022 |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | BUILD |  |  |  |  |  |  | LEASING |  | ACQUISTIONS |  |  |  |
| Year | LA New Build | AHB New Build | Part V New Build | PPP Build | JV Build | Total New Build | DHLGH Build Target | Leasing Total | DHLGH Leasing Targets | LA | AHB | Total |
| 2020 | 0 | 156 | 108 | 109 | 0 | 373 | 467 | 119 | 120 | 13 | 20 | 33 |
| 2021 | 2 | 137 | 108 | 0 | 0 | 247 | 245* | 159 | 150* | 3 | 1 | 4 |
|  | Original DHLGH Target |  |  |  |  |  | 408 |  | 190 |  |  |  |  |

* 2021 pipeline revised due to impact on programme of delivery during Level 5 restrictions.

| Capital Housing Delivered 2021 – per LEA |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| LEA | LA Build | AHB Build | Part V | Total Build | LA Acquis | AHB Acquis | Total Acquis. | Total Leasing | Grand Total |
| Clondalkin | 0 | 14 | 14 | 28 | 0 | 0 | 0 | 36 | 64 |
| Lucan | 0 | 90 | 49 | 139 | 1 | 0 | 1 | 15 | 155 |
| Tallaght Central | 0 | 0 | 1 | 1 | 0 | 1 | 1 | 26 | 28 |
| Tallaght South | 0 | 22 | 34 | 56 | 1 | 0 | 1 | 62 | 119 |
| Rathfarnham/Templeogue | 0 | 11 | 1 | 12 | 0 | 0 | 0 | 8 | 20 |
| Palmerstown/Fonthill | 2 | 0 | 0 | 2 | 0 | 0 | 0 | 12 | 14 |
| Firhouse/Bohernabreena | 0 | 0 | 9 | 9 | 1 | 0 | 1 | 0 | 10 |
| Grand Total | 2 | 137 | 108 | 247 | 3 | 1 | 4 | 159 | 410 |

| HOUSING FOR ALL TARGETS 2022 |  |  |  |
| --- | --- | --- | --- |
| Year | Build | Leasing | Total SDCC Target 2022 |
| 2022 | 400 | 40 | 440 |

|  | Capital Housing Delivery Comparison Years 2020 and 2021 Clondalkin |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Area |  | LA New Build | AHB New Build | PPP Build | Part V New Build | Total New Build | LEASING TOTAL | Acquisitions Total | Total PA Delivered Units |
| Clondalkin 2020 |  | 0 | 148 | 109 | 24 | 281 | 43 | 7 | 331 |
| Clondalkin 2021 |  | 0 | 14 | 0 | 14 | 28 | 36 | 0 | 64 |

| Construction Programme 2022 |  |  |  |  |
| --- | --- | --- | --- | --- |
| Projects with Part 8 Planning Approval |  |  |  |  |
| Local Electoral Area | Project Name | Part 8 Approved Date | No. of Units Approved @ Part 8 | Current Status |
| Clondalkin | Riversdale | 08/10/2018 | 44 | Phase 1 of 25 units under construction with projected delivery Q4 2022. Previously 22 units now up to 25. Phase 2 currently under review. |
| Clondalkin | Nangor Road (Eircom Site) | 14/10/2019 | 93 | Stage 4 funding approval granted December 2021. Appointing contractor January 2022. |
| Clondalkin | Lindisfarne, Clondalkin | 11/01/2021 | 19 | Tender process underway. |
|  |  |  | 156 |  |

| Next tranche of Proposed Part 8’s |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Scheme Location | Local Electoral Area | Proposed no. of Social Units | Proposed no. of Affordable Units | Total Number of Units in Scheme | Status |
| Clonburris Phase 2 | Clondalkin | 56 | 57 | 113 | Detailed design underway. Proposal to ACM February 2022. |

| Part V Delivery Programme for 2022 |  |  |
| --- | --- | --- |
| Scheme Name | No. of Units | Status of Part V Agreement |  |
| Sallypark, New Nangor Road, Clondalkin | 8 | Part V agreement in place. Clúid Housing acquiring the full scheme which will deliver 85 units specific for Older Persons. Due for completion June 2022. |  |
| Graydon, Newcastle | 15 | Part V agreement in place. |  |
| Ballynakelly Roundabout | 1 | Part V agreement in place. |  |
| Cornerpark, Newcastle | 1 | Agreement in place. Novas Arlington AHB nominated to acquire and unit is due for delivery Q2 2022. |  |
| Total | 25 |  |  |

| Part V Agreements in Place |  |  |
| --- | --- | --- |
| Scheme Name | No. of Units | Status of Part V Agreement |  |
| San Guida, New Road, Clondalkin | 2 | Agreement in place with Clúid Housing to deliver the total scheme of 24 units. Projected delivery 2023. |  |
| Grand Total | 2 |  |  |