## Slide 1
Rathfarnham Castle Outbuildings
Business Model & Procurement Approach

## Slide 2
Overall Layout

## Slide 3
North Courtyard 1 & 2

## Slide 4
Business Model & Procurement
SDCC
Asset Management
Building
Capital Budget: €5m
Design & Build
Operational Partner
Rental Income
Operational Partner
Proven Track Record
Appropriate Use(s)
Building Fit-out
Long-term Lease
Building Operations
Design Partner
Development Opportunity
Mixed Use
Hospitality
Retail
Food
Lifestyle
Procurement
Prior Information Notice
Stage 1:
Prequalification
Stage 2: Competitive Dialogue

## Slide 5
Building Design
Concept Drawing
Floor Area c.1,400 sq. metres

## Slide 6
Market Examples

## Slide 7
Catchment Area
32,000 People within 1km of Rathfarnham Castle & Outbuildings
Cycling & Walking
Connectivity to Other Amenities
Cark Parking

## Slide 8
Work Activity | Date
Prior Information Notice Issued | March 2022
Stage 1 Operator expression of interest process complete | May 2022
Commence procurement process for building design consultants | June 2022
Stage 2 tender for operator complete | September 2022
Building design consultants appointed | September 2022
Part 8 Agreed | June 2023
Construction contractor appointed | November 2023
Construction start date | January 2024
Construction project completion | January 2025
Indicative Project Timeline