COMHAIRLE CONTAE ÁTHA CLIATH THEAS
SOUTH DUBLIN COUNTY COUNCIL

Clondalkin Area Committee Meeting

20th April 2022

HEADED ITEM NO.8

Q1 2022 Housing Supply Programme Quarterly Report

| CAPTIAL HOUSING DELIVERY 2020-2022 |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | BUILD |  |  |  |  |  |  | LEASING |  | ACQUISTIONS |  |  |  |
| Year | LA New Build | AHB New Build | Part V New Build | PPP Build | JV Build | Total New Build | DHLGH Build Target | Leasing Total | DHLGH Leasing Targets | LA | AHB | Total |
| 2020 | 0 | 156 | 108 | 109 | 0 | 373 | 467 | 119 | 120 | 13 | 20 | 33 |
| 2021 | 2 | 137 | 108 | 0 | 0 | 247 | 245* | 159 | 150* | 3 | 1 | 4 |
|  | Original DHLGH Target |  |  |  |  |  | 408 |  | 190 |  |  |  |  |

* 2021 pipeline revised due to impact on programme of delivery during Level 5 restrictions.

| Capital Housing Delivered 2021 – per LEA |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| LEA | LA Build | AHB Build | Part V | Total Build | LA Acquis | AHB Acquis | Total Acquis. | Total Leasing | Grand Total |
| Clondalkin | 0 | 14 | 14 | 28 | 0 | 0 | 0 | 36 | 64 |
| Lucan | 0 | 90 | 49 | 139 | 1 | 0 | 1 | 15 | 155 |
| Tallaght Central | 0 | 0 | 1 | 1 | 0 | 1 | 1 | 26 | 28 |
| Tallaght South | 0 | 22 | 34 | 56 | 1 | 0 | 1 | 62 | 119 |
| Rathfarnham/Templeogue | 0 | 11 | 1 | 12 | 0 | 0 | 0 | 8 | 20 |
| Palmerstown/Fonthill | 2 | 0 | 0 | 2 | 0 | 0 | 0 | 12 | 14 |
| Firhouse/Bohernabreena | 0 | 0 | 9 | 9 | 1 | 0 | 1 | 0 | 10 |
| Grand Total | 2 | 137 | 108 | 247 | 3 | 1 | 4 | 159 | 410 |

| HOUSING FOR ALL TARGETS 2022 |  |  |  |
| --- | --- | --- | --- |
| Year | Build | Leasing | Total SDCC Target 2022 |
| 2022 | 400 | 40 | 440 |

| Capital Housing Delivered Year to Date 2022 |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Area | LA New Build | AHB New Build | Part V New Build | Total New Build | LEASING TOTAL | Acquisitions Total | Total Delivered Units |
| Clondalkin | 0 | 0 | 0 | 0 | 3 | 0 | 3 |

| Clondalkin LEA Capital Housing due for delivery 2022 |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Project | LA New Build | LA Mixed Tenure – Social | LA Mixed Tenure – Affordable purchase | AHB new build | Part V New Build | AHB Cost Rental | Total |
| Kilcarbery |  | 73 | 16 | 0 | 0 | 74 | 163 |
| Riversdale | 25 | 0 | 0 | 0 | 0 | 0 | 25 |
| Sallypark | 0 | 0 | 0 | 77 | 8 | 0 | 85 |
| Graydon, Newcastle | 0 | 0 | 0 | 0 | 15 | 0 | 15 |
| Ballynakelly, Newcastle | 0 | 0 | 0 | 0 | 1 | 0 | 1 |
| Cornerpark, Newcastle | 0 | 0 | 0 | 0 | 1 | 0 | 1 |
| Total | 25 | 73 | 16 | 77 | 25 | 74 | 290 |

| Construction Programme 2022 |  |  |  |  |
| --- | --- | --- | --- | --- |
| Projects with Part 8 Planning Approval |  |  |  |  |
| Local Electoral Area | Project Name | Part 8 Approved Date | No. of Units Approved @ Part 8 | Current Status |
| Clondalkin | Riversdale | 08/10/2018 | 43 | Phase 1 of 25 homes on site & due for practical completion by June 2022. Contractor appointed for invasive species removal works for phase 2. Entire scheme 43 units in total. |
| Clondalkin | Nangor Road (Eircom Site) | 14/10/2019 | 93 | Site works commenced in March 2022 with projected practical completion by September 2023. |
| Clondalkin | Lindisfarne, Clondalkin | 11/01/2021 | 19 | Tenders being assessed to prepare Stage 4 DHLGH funding report and to appoint contractor. |
|  |  |  | 156 |  |
| Mixed Tenure Development – Kilcarbery |  |  |  |  |
| Local Electoral Area | Project Name | Project status | No. of Units approved | Current Status |
| Clondalkin | Kilcarbery | On site | 50 | Affordable purchase units – 16 due for delivery 2022 |
| Clondalkin | Kilcarbery | On site | 310 | Phase 1 – 112 units, 73 units due for delivery 2022. |

| Next tranche of Proposed Part 8’s |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Scheme Location | Local Electoral Area | Proposed no. of Social Units | Proposed no. of Affordable Units | Total Number of Units in Scheme | Status |
| Clonburris Phase 2 (Canal End Extension | Clondalkin | 56 | 62 | 118 | Part 8 published 31st of March 2022. Public consultation open for submissions until 17th of May 2022. |

| Part V Delivery Programme for 2022 |  |  |
| --- | --- | --- |
| Scheme Name | No. of Units | Status of Part V Agreement |  |
| Sallypark, New Nangor Road, Clondalkin | 8 | Part V agreement in place. Clúid Housing acquiring the full scheme which will deliver 85 units specific for Older Persons. Due for completion Q3 2022. |  |
| Graydon, Newcastle | 15 | Part V agreement in place. Units due for delivery Q3 2022 |  |
| Ballynakelly Roundabout | 1 | Part V agreement in place. Due for delivery end Q2 2022 |  |
| Cornerpark, Newcastle | 1 | Agreement in place. Novas Arlington AHB nominated to acquire and unit is due for delivery Q2 2022. |  |
| Total | 25 |  |  |

| Part V Agreements in Place |  |  |
| --- | --- | --- |
| Scheme Name | No. of Units | Status of Part V Agreement |  |
| San Guida, New Road, Clondalkin | 2 | Agreement in place with Clúid Housing to deliver the total scheme of 24 units. Projected delivery 2023. |  |
| Grand Total | 2 |  |  |