## Sheet1
TALLAGHT CENTRAL
Project | Votes Cast | Funding Amount | Status | Dept.
Sensory garden / accessible playground | 727 | 20000 | Accessible bench and sculpture (sensory play feature) surrounded by pollinator planting being designed currently. | EWCC
Improve the Kingswood playground | 607 | 30000 | Design completed and due to commence construction shortly | EWCC
Native tree trail in Sean Walsh Park | 528 | 10000 | In the process of procuring tree trail signage and we are examining what is needed to link the proposed tree trail signage in with information contained on the Council website. We also expect to progress this project before the end of the year. | EWCC
Signage for viewing points of the Dublin Mountains | 522 | 5000 | Currently in Initial planning stages within the department | EETD
Upgrade the playground at Aylesbury Field | 511 | 40000 | Completed | EWCC
Fruit Trees along Bolbrook Stream and Avonmore Road | 503 | 5000 | Plan is it will be done during the winter tree planting season (November to February). | EWCC
Basketball and tennis court in Kilnamanagh | 501 | 60000 | Currently in Initial planning stages within the department - waiting for update | HSCD
Outdoor event space in Sean Walsh Park | 499 | 35000 | Currently examining various options in relation to this. We expect to progress this before the end of year. | EWCC
Toddler specific playground for Old Bawn | 476 | 30000 | Tendered for and due to commence construction shortly | EWCC
Upgrade the playground at Sean Walsh Park | 471 | 50000 | Due to commence in the coming weeks. | EWCC
Signage for Tallaght waterway | 458 | 10000 | Currently in Initial planning stages within the department | LUPT
A book of short stories and poetry | 325 | 2000 | Completed | EETD
Total |  | 297000