COMHAIRLE CONTAE ÁTHA CLIATH THEAS
SOUTH DUBLIN COUNTY COUNCIL

MEETING OF Rathfarnham/Templeogue-Terenure Area Committee

**Tuesday, October 11th, 2022**

**HI14**

**UPDATE TO THE LED ENERGY EFFICIENCY PROGRAMME/SOX MAINTENANCE**

**ESBN Supplemental Agreement**

The ESBN Supplemental Agreement has been agreed and the SDCC Legal Representatives are liaising directly with the ESBN Legal Section on the correct procedure to Seal the Agreement. Once this is agreed between both Legal teams, the agreement will be presented to the County Manager for signing.

In the meantime, we have agreed 3 No. Estate to be upgraded to trial the co-ordinated works procedures between the SDCC Contractor Work Crews and the ESBN Network Technicians. There will be one estate upgraded in each ESBN Area, Dublin South, Dublin Central and Dublin Central. These Estates are Rathfarnham Wood, Rathfarnham, Redwood, Kilnamanagh and Ashwood, Clondalkin.

Significant progress has been made with the National Public Lighting Interface Officer in the ESBN in agreeing work processes and information transfer between SDCC and the ESBN. ESBN has agreed in principle to provide resources to advance the next stage of the SDCC LED Upgrade Works. ESBN Area Managers are identifying resources to assign to these project works.

However, we have not yet upgraded any LEDS under this Supplemental Agreement and this is a significant delay to our programme. We are continuing to push the ESBN to progress to full scale mobilisation as quickly as possible to minimise any further delays.

**Maintenance of remaining SOX lanterns**

27% of the 9724 lanterns in the RTFB area are SOX lanterns. This comes to 2680 SOX lanterns. As previously stated, manufacture of SOX lamps halted in 2018. SDCC bulk bought a 4-year supply of lamps to service maintenance needs. These lamps have supplied our maintenance needs to date, but are now all in use.

We also have a programme of “harvesting” lamps and other equipment from the SOX lanterns decommissioned during our LED Upgrades. The delay in bringing the ESBN SA Programme to operational stage has impacted this “cannibalisation” of our stock. To supplement this, we have sourced an additional 500 SOX lamps on the market. This is sufficient to service our expected maintenance needs until the ESBN SA Programme is “live” and our “harvesting” programme will then continue to supply our SOX repairs.