## Sheet1
CLONDALKIN
Project | Funding Amount | Status | Dept. Assigned
Pedestrian Link between the Round Tower and Corkagh Park | 40000 | Paused - funding allocated not sufficient upon initial research. It is the intention to deliver under the Corkagh to Grand Canal (via Clodalkin) under the Active Travel Scheme. NTA funded scheme to be initiated in 2023 | LUPT
Renovate Portocabin for the Clondalkin Men Shed | 7000 | Complete | HSCD
Restoration of Old Nangor Road Water Pump | 1000 | Complete | EETD
New Christmas Lights for Clondalkin Village | 20000 | Complete | HSCD
A Community Orchard, Clondalkin Electoral Area | 10000 | Complete | EWCC
Irish Signs for Clondalkin | 3200 | Paused | LUPT
Planting Flowers across the Bawnogue Area | 5000 | Complete | EWCC
Safety and Inclusivity Study of Clondalkin's Public Spaces | 50000 | Complete | https://www.sdcc.ie/en/have-your-say/past-winners/clondalkin/safety-and-inclusivity-study-of-clondalkin-s-public-spaces/safety-and-inclusivity-study-of-clondalkin-public-spaces.pdf
On-Street Bicycle Pump, Clondalkin Villlage | 3500 | Complete | LUPT
Bottle banks and recycling facilities for Cherrywood | 20000 | Not Complete - A suitable site could not be found in the area for the proposed bottle banks for Cherrywood so this could not proceed | EWCC
WiFi Activated Self-Guided Historical Trail of Clondalkin | 30000 | Complete
New Play Ground, Forest Hill Estate | 60000 | On Going | EWCC
Acoustic Piano for the Rathcoole Community Centre | 5000 | Not Complete - construction was ongoing at community centre which paused plans - funding not drawn down as of yet and is still available to draw down | HSCD
Gym Equipment and Activities for Rathcoole Community Centre | 25000 | Complete | HSCD
Welcome to Clondalkin Hedge Signage | 20000 | Not Complete | EWCC
Total | 299700