## Slide 1: R4 Strategic Noise Mapping and Noise Action Plans Agglomerations Environment and Climate Action SPC Meeting. 7th February 2023 David O’ Brien Principal Env. Health Officer

## Slide 2
Round 4 Strategic Noise Mapping and Noise Action Plan Overview
National Approach to Round 4
Milestones and Progress to Date
Strategic Noise Modelling Results – Dublin
Next Steps
Questions / Discussion

## Slide 3
European Communities (Environmental Noise) Regulations 2018 (S.I. 549/2018)
The Regulations give effect to the Environmental Noise Directive (END) 2002/49/EC
Apply to environmental noise, created by human activities, which people are exposed to; in built-up areas, in public parks/quiet areas, near schools & hospitals and other noise-sensitive buildings/areas.
Essentially it relates to road transport, trains and Luas, aircraft and industries
We are now in Round 4 and each round applies for 5 consecutive years
Maps are to be Clear, Comprehensive and Accessible

## Slide 4
The Regulations/END requires the following two indicators to be applied in the assessment :-
  Lden is the annual average noise level for the day, evening and night period and is designed to measure ‘annoyance’.
  It has a defined threshold of 55dB.
  Lnight is the annual average noise level for night-time periods and is designed to assess sleep disturbance.
  It has a defined threshold of 50dB.
Member States must report on the numbers of people who are exposed to noise levels above these thresholds for a range of noise sources.

## Slide 5
European Communities (Environmental Noise) Regulations 2018 (S.I. 549/2018)
The EPA in Ireland is the national competent authority for the purpose of overseeing implementation and for providing guidance.
The Regulations require Noise Mapping Bodies (NMBs) to prepare or review Strategic Noise
Agglomerations (>100,000 persons) (road, rail, airports & industry)
      Major roads (>3,000,000 vehicle passages per year)
      Major rail (>30,000 train passages per year)
      Major airport (>50,000 movements per year)
The Regulations require Action Planning Authorities (APAs) to make or review Noise Action Plans
Maps - Completed 2022 and are being published by the end of this month (February 2023)

## Slide 6
  Round 4 – new National approach was adopted;
  Dublin, Cork and Limerick were amalgamated into Super Agglomeration
  A Noise consultant was appointed to complete the noise modelling and mapping.
  Major Roads and Rail outside agglomerations – Transport Infrastructure Ireland (TII) would complete the noise modelling and mapping.
  Major Airports – Dublin Airport Authority (DAA), complete the noise modelling and mapping.

## Slide 7
  New additions to Round 4 included
    Celbridge and Leixlip are joined with SDCC boundary.
    Bray is joined with Dun Laoghaire Rathdown.
    Limerick City also in for first time
    Dublin and Cork Ports measured.
  Other state agencies include :
  Transport Infrastructure Ireland (TII)
  Irish Rail and Luas
  Road Management Office (RMO)
  National Transport Authority (NTA)
  DAA

## Slide 8
Progress Task | Timelines
Completed data register and major data collection exercise | June 2021 - March 2022
Completed tender documents and published contract notice for Consultant | 18th February 2022
Appointed project consultant and commenced project - Phase 1 – Noise Mapping | 26th May 2022
Weekly co-ordination meetings with TII on modelling of major roads at agglomeration boundaries including modelling of pilot area on M11 | August – September 2022
Commenced noise modelling Limerick Cork & Dublin | 27th October 2022 28th October 2022
Provided draft model outputs results to Local Authorities Cork & Limerick - All sources & Exposure Statistics, Dublin – Road only Dublin - Industry Dublin – Rail Dublin Exposure Statistics (all sources) | 25th November 2022 29th November 2022 2nd December 2022 7th December 2022
Prepare model results in line with EPA/EEA reporting requirements and deliver to EPA Note: Issues with uploading reports to EEA ReportNet site have been encountered but this is due to issues with the reporting site and is being dealt with by the EPA. | 9 – 16th December 2022

## Slide 9: Dublin Strategic Noise Modelling Results – Roads Lden

## Slide 10: Dublin Strategic Noise Modelling Results – Roads Lnight

## Slide 11: Dublin Strategic Noise Modelling Results – Rail Lden

## Slide 12: Dublin Strategic Noise Modelling Results – Rail Lnight

## Slide 13: Dublin Strategic Noise Modelling Results – Industry Lden

## Slide 14: Dublin Strategic Noise Modelling Results – Industry Lnight

## Slide 15
Phase 1 Deliverable | Programme Delivery Date
Finalise Graphical Strategic Noise Maps (Limerick, Cork & Dublin) | January /February 2023
Data Review, Evaluation and Model Set-up Reports (Limerick, Cork & Dublin) | January to April 2023
Noise Model Files (Limerick, Cork & Dublin) | January 2023
Noise Modelling and Exposure Assessment Report (Limerick, Cork & Dublin) | April to May 2023
Maps Available to the Public (Limerick, Cork & Dublin) | February 2023

## Slide 16
Phase 2 Deliverable | Indicative Timeline
Commence Phase 2 | June 2023
Draft Noise Action Plans | Q4 2023
SEA / AA | Q4 2023 – Q1 2024
Public Consultation | Q1 2024
Final Noise Action Plans | Q2 2024
Deliver Final Noise Action Plans to EPA | Q3 2024
EEA Deadline | End 2024

## Slide 17: Conclusions
New calculation system is better & will have more interactive website
Oden system should allow users to zoom around and get information
There will be a range of maps incorporating all 10 counties involved
Next phase to develop and assess new noise reduction measures
Quiet Areas will be completed and increased in number.