## Firhouse Bohernabreena
Firhouse - Bohernabreena
Project | Votes Cast | Funding Amount | Dept. Assigned | Status
Health and Wellbeing Garden in Firhouse Community Centre | 1519 | 100000 | HSCD | Paused - due to work that were ongoing
Intergenerational Outdoor Activity Spaces in Glenasmole | 1472 | 140000 | EWCC | Awaiting notification from Glenasmole local community regarding completion of their works on this site and when they wish us to commence the project. Partial draw down for project already happened. Final works to be completed before remainder can be actioned. Approx 37k drawn down. €104,627.72 left to be drawn down
Nature Trail along the river Dodder | 926 | 20000 | EWCC | Complete
Playground Facilities at Ballycragh Park | 782 | 20000 | EWCC | Complete - Extension complete Q3 2022
Native Tree Trail in Woodlawn Park | 767 | 10000 | EWCC | Complete
Total |  | 290000

## Rathfarnham Templeogue
RATHFARNHAM TEMPLEOGUE
Project | Votes Cast | Funding Amount | Status | Dept. Assigned
A nature trail in Rathfarnham Castle Park | 1214 | 30000 | Not done as of yet - to be progressed 2023 | EWCC
Planting fruit trees throughout the Rathfarnham Templeogue electoral area | 1208 | 20000 | fruit trees have been ordered as part of the Tree Planting. This planting is due to take place in 2023 subject to site selection | EWCC
Green laneways for Rathfarnham | 1165 | 10000 | Not Completed/Paused - reply sent to submitter | LUPT
Christmas lights for Templeogue Village and Rathfarnham Village | 1115 | 70000 | Lights were supplied for Rathfarnham late Dec 2023. Templeogue to arrange lights for 2023. Money still with corporate. Expecting draw downs for payment to happen early 2023 - split agreed by parties 40k Rath - 30k Temple (updated 30.1.23) | HSCD
Outdoor nature classrooms on local greens | 1085 | 25000 | To be programmed for design and procurement 19/10/22 | EWCC
A bicycle pump for Templeogue Village | 952 | 5000 | Completed - SEPT 22 | LUPT
Run a STEAM (Science, Technology, Engineering, Arts, Mathematics) Project for children from the Traveller Community | 811 | 5000 | STEAM project is to get up and running this quarter (Q1 2023) | EETD
Drinking water stations for Rathfarnham | 737 | 50000 | Contract in place - Not progressed as of yet - site selection to begin | EWCC
Place QR code stands near Templeogue Cemetery and the nearby Old Church | 656 | 10000 | Project currently planned in conjunction with county wide Hostorical trail and interactive app | EETD
Run a poetry competition in Rathfarnham | 440 | 2000 | The poetry competition will be run in March/April to coincide with World Poetry Day and Poetry Day Ireland | EETD
New seating for the Crannagh Road area | 358 | 10000 | Not progressed as of yet | EWCC
Playground and seating for the College Drive/Fortfield Road | 313 | 60000 | To be programmed for design and procurement 19/10/22 | EWCC
Total |  | 297000