## Sheet1
TALLAGHT CENTRAL
Project | Votes Cast | Funding Amount | Status | Contact
Sensory garden / accessible playground | 727 | 20000 | Sculpture completed. Installation of sculpture and accessible bench to commence shortly - Q1 | EWCC
Improve the Kingswood playground | 607 | 30000 | Complete | EWCC
Native tree trail in Sean Walsh Park | 528 | 10000 | Procurement in place, currently examining tree trail locations. | EWCC
Signage for viewing points of the Dublin Mountains | 522 | 5000 | There are construction works (Older Persons Homes) currently underway in the vicinity of the likely location for such signage in Sean Walsh Park. Once works are complete, the department will begin discussions with the Public Realm section in order further this proposal. | EETD
Upgrade the playground at Aylesbury Field | 511 | 40000 | Completed | EWCC
Fruit Trees along Bolbrook Stream and Avonmore Road | 503 | 5000 | Due to be completed by the 24th Feb | EWCC
Basketball and tennis court in Kilnamanagh | 501 | 60000 | Local Community Groups have rejected the winning project. Submission was not made by a community group. Funding remains unused | HSCD
Outdoor event space in Sean Walsh Park | 499 | 35000 | The operations team have viewed and assessed canopies in DLR & DCC. Based on finding/ lessons learned we are currently in concept design phase of the project. | EWCC
Toddler specific playground for Old Bawn | 476 | 30000 | Completed Dec 22 | EWCC
Upgrade the playground at Sean Walsh Park | 471 | 50000 | Completed - Jan 23 | EWCC
Signage for Tallaght waterway | 458 | 10000 | Currently in Initial planning stages within the department | EETD
A book of short stories and poetry | 325 | 2000 | Completed | EETD
Total |  | 297000

## Sheet2
|  |  | Update Oct 22 |  |  | Update Feb 2023
Sensory garden / accessible playground | 727 | 20000 | Sculpture completed. Installation of sculpture and accessible bench to commence shortly - Q1 | Suzanne Furlong | EWCC | Sculpture completed. Installation of sculpture and accessible bench to commence shortly - Q1
Improve the Kingswood playground | 607 | 30000 | Tender completed, at lead in period. Construction to commence when ground conditions improve | Suzanne Furlong | EWCC | Complete
Toddler specific playground for Old Bawn | 476 | 30000 | Completed Dec 22 | Suzanne Furlong | EWCC | Complete
Upgrade the playground at Aylesbury Field | 511 | 40000 | Completed | Suzanne Furlong | EWCC | Complete
Fruit Trees along Bolbrook Stream and Avonmore Road | 503 | 5000 | 15no. fruit trees have been ordered as part of the Tallaght area Tree Planting. This planting is due to take place in Q1 of 2023 February/March in planting season | Leo Magee/ Damien Wildes | EWCC | Due to be completed by the 24th Feb
Outdoor event space in Sean Walsh Park | 499 | 35000 | Currently examining various options in relation to this. Options being reviewed as initial budget assigned proving to be an obstactle due to increased costs | Leo Magee/ Sophie/ Brendan | EWCC | The operations team have viewed and assessed canopies in DLR & DCC. Based on finding/ lessons learned we are currently in concept design phase of the project.
Native tree trail in Sean Walsh Park | 528 | 10000 | In the process of procuring tree trail signage and we are examining what is needed to link the proposed tree trail signage in with information contained on the Council website. Team have been actively looking to speak to members of the St. Martins residents group who made the submission to no avail | Leo Magee/ | EWCC | Procurement in place, currently examining tree trail locations.
Damien Wildes
Signage for viewing points of the Dublin Mountains | 522 | 5000 | Currently in Initial planning stages within the department | Ralph McGarry | EETD
Basketball and tennis court in Kilnamanagh | 501 | 60000 | Local Community Groups have rejected the winning project. Submission was not made by a community group. Funding remains unused | Paul McAnerny | HSCD
Signage for Tallaght waterway | 458 | 10000 | Currently in Initial planning stages within the department |  | EETD
A book of short stories and poetry | 325 | 2000 | Completed | Paul Fusco | EETD