## Sheet1
CLONDALKIN
Project | Funding Amount | Status | Dept. Assigned
Pedestrian Link between the Round Tower and Corkagh Park | 40000 | Paused - funding allocated not sufficient upon initial research. It is the intention to deliver under the Corkagh to Grand Canal (via Clodalkin) under the Active Travel Scheme. NTA funded scheme to be initiated in 2023 | LUPT
Renovate Portocabin for the Clondalkin Men Shed | 7000 | Complete | HSCD
Restoration of Old Nangor Road Water Pump | 1000 | Complete | EETD
New Christmas Lights for Clondalkin Village | 20000 | Complete | HSCD
A Community Orchard, Clondalkin Electoral Area | 10000 | Complete | EWCC
Completed - in Line with Heritage App | 3200 | Complete | LUPT
Planting Flowers across the Bawnogue Area | 5000 | Complete | EWCC
Safety and Inclusivity Study of Clondalkin's Public Spaces | 50000 | Complete | https://www.sdcc.ie/en/have-your-say/past-winners/clondalkin/safety-and-inclusivity-study-of-clondalkin-s-public-spaces/safety-and-inclusivity-study-of-clondalkin-public-spaces.pdf
On-Street Bicycle Pump, Clondalkin Villlage | 3500 | Complete | LUPT
Bottle banks and recycling facilities for Cherrywood | 20000 | Not Complete - A suitable site could not be found in the area for the proposed bottle banks for Cherrywood so this could not proceed | EWCC
WiFi Activated Self-Guided Historical Trail of Clondalkin | 30000 | Complete
New Play Ground, Forest Hill Estate | 60000 | Our engagement (pre covid) with the local resident’s association was not generally in favour of the proposal. We committed to further consultation but Covid intervened. Since then; we tried to re-engage with the local residents association but there is no response. We are awaiting a response to our query regarding updated residents association contacts. If the Councillors would like to advise re any new contacts in the area that they know of; it would be gratefully received. | EWCC
Acoustic Piano for the Rathcoole Community Centre | 5000 | Not Complete - construction was ongoing at community centre which paused plans - funding not drawn down as of yet and is still available to draw down | HSCD
Gym Equipment and Activities for Rathcoole Community Centre | 25000 | Complete | HSCD
Welcome to Clondalkin Hedge Signage | 20000 | Not Complete - The project was “to construct a ‘Welcome to Clondalkin’ greeting at Newlands Cross. This will be a mound with the words made with shrubs, such as box hedging, to provide a warm welcome to those entering Clondalkin”. Based on examination of a similar ‘hedge signs’, the dimension of the hedge would need to be approximately 15 metres long x 5 metres high. All grass verges on Fonthill Road between Boot Road and the N7 were examined for suitability. The largest area available was on the north east side of the Fonthill Road/N7 junction near the 1916 garden. This site is on the outbound side of the Fonthill Road as you exit Clondalkin. A hedge on this site would not have been visible to Clondalkin inbound traffic and was therefore unsuitable. Other locations examined were at the back/side of Newlands Cross Garden Centre and the area between the Circle K and St Brigid’s Well. Neither site had sufficient space available. There were no other locations of sufficient size to accommodate the hedge in the area examined. | EWCC
Total | 299700