## Slide 1
Housing Delivery Update Report Housing Strategic Policy Committee Meeting 30th May 2023

## Slide 2: 2023
Notes: textbox
No alt text provided
Housing for All Delivery Pipeline 2023
No alt text provided
No. of Potential Units Per LEA
No alt text provided
image
No alt text provided
tableEx
No alt text provided

## Slide 3
LEA | Site | No. | Update
Clondalkin | Mayfield/Riversdale Phase 2 * | 18 | On site-due for completion Q4 2023
 | New Nangor Rd. (”Eircom” site) * | 93 | On site-due for completion Q4 2023
 | Old Nangor Rd. (Simon) | 10 | Revised planning application- additional information sought
 | New Road Clondalkin (Pt V) | 2 | Part V negotiations to commence
 | Watery Lane (Pt V) | 6 | Part V to be agreed/ non engagement by developer
 | Clonburris Private (Pt V) | 30 | On site Part V to be agreed/delivery est. 2024
 | St Finians Way, Newcastle | 1 | On site, Part V engagement underway, delivery 2024
 | Gordon Pk/Clondalkin Rugby Club (Pt V) | 7 | Part V to be agreed/delivery est. 2024
 | Parklands Ph1 Citywest | 23 | On site-due, due for delivery 2024
Rathfarnham/Templeogue | Garretstown House/Laurel Manor (Pt V) | 2 | Part V to be agreed/delivery est. 2024
Firhouse/Bohernabreena | Homeville * | 16 | Tender assessment to appoint contractor underway – 2024 delivery
 | Pearse Brothers Park * | 10 | Tender for contractor to be advertised Q3 2023
Approved/Proposed Developments by LEA (1)
Notes: * Denotes SDCC owned site

## Slide 4
LEA | Site | No. | Update
Tallaght Central | Old Bawn * | 12 | On site-due for completion Sept ‘23
 | Fernwood/Maplewood (Clúid) | 40 | Est. completion Maplewood June, Fernwood August ‘23
 | Whitestown Way (Clúid) | 81 | On site-due for completion Dec 2023
 | Mountain Gate (Part V) | 7 | On site-due for completion November 2023
 | Airton Plaza (Part V) | 30 | Part V negotiations ongoing, delivery 2025
 | Former Gallaghers Site (Airton/Greenhills Rd) Part V | 50 | Part V negotiations have commenced, delivery expected 2025
 | St. Aongus’ Green | 10 | Tender for contractor to be advertised Q3 2023
Tallaght South | Rossfield * | 12-16 | Planning derogation to be advertised June23
 | Citywest View (Cooldown Commons Ph3) Part V) | 36 | Part V negotiations underway, potential delivery Q4 2023, and Q1 & Q2 2024
Lucan | Aderrig Ph 2 (Pt V) | 21 | On site due for delivery 2024
 | St Helens Plaza (Pt V) | 4 | On site-due for completion 2024
 | St Edmunds (Pt V - TAU Fonthill) | 7 | Part V agreed – on site, delivery Dec ‘23
 | Adamstown Station/District Centre (Pt V) | 74 | Part V units various phases/delivery from 2024
 | Clonburris Private (Pt V) | 56 | Part V to be agreed/potential delivery from late 2024
Palmerstown/Fonthill | Balgaddy * | 69 | Contractor on site, delivery 2024
 | Old Lucan Rd (Túath) | 4 | SDCC investigating acquiring adjacent strip of land.
 | St. Ronan’s * | 9 | Design team appointed/Contractor tender Q3 2022/ Delivery 2024
 | Cloverhill (Pt V) | 4 | On site-due for completion June 2023
Approved/Proposed Developments by LEA (2)
Notes: * Denotes Council owned site

## Slide 5
SDCC-owned Large Sites
Kilcarbery: 1,034 homes with 30% social (310 homes)
Projected delivery of 103+ social and 29 discounted/affordable purchase homes in 2023, scope for further social homes. Developer submitting revised planning permission to add additional floor to two apartment blocks
Killinarden: 620 homes (including 125 social & 372 affordable purchase).
Planning approval received, Developer anticipates being on site before end of Summer, projected delivery from 2024
Clonburris: Phases 1 & 2 comprising 382 homes (149 social), Phases 3,4,5 with potential for 1,600 homes (40% social)
Tender to appoint mutli-disciplinary design teams for Phases 3,4 & 5 closed 22/5/23, currently under assessment. Tender for contractor Ph 2 (CA) – Closed May, currently under assessment. Tender for Phase 1 to be advertised June 2023 Proposed PPP site comprising 120 social homes–Section 85 approved Feb 2023 – DT appointed. Topo/SI surveys to be undertaken over Summer months.
Belgard Square North: 133 cost rental apartments
Contractor commenced on site April’23. Delivery estimated March 2025.
Rathcoole: Number of homes & tenure mix to be confirmed
Revised masterplan currently being finalised which includes social, TA and scope for affordable housing to be examined

## Slide 6: Council owned sites to be progressed in 2023 / Avail of Planning Derogation
Location | Est. No. Units | LEA | Status | Next Action | Timeline
Rossfield | 15 | Tallaght South | Planning | Advertise scheme for planning | Q2 2023
Alpine Heights | 12-15 | Clondalkin | Feasibility Report | ACM Feb 23 | Q1 2023
Deansrath/Melrose | 25 | Clondalkin | Planning | Advertise scheme June 23 | Q2 2023
Kilcarbery 2 | 22 | Clondalkin | Feasibility Report | Concept design to April 23 ACM | Q2 2023
Old Castle Clondalkin | 50 | Clondalkin | Prepare scheme for planning | ACM Dec 22/ Design being progressed for planning | Q3 2023
Castlefield | 10 | Firhouse/Boherna. | Feasibility Report | ACM Feb 23/progress to planning | Q1 2023
Stocking Lane | 15 | Firhouse/Boherna. | Feasibility Report | ACM Feb 23/progress planning | Q1 2023
Sarsfield Park, Lucan | 6 | Lucan | Feasibility report | Concept design ACM April 23 | Q2 2023