## Slide 1
Housing Delivery Update Report Clondalkin, Newcastle, Rathcoole, Saggart and Brittas Area Committee Meeting 20th September 2023

## Slide 2: 2023
Notes: textbox
No alt text provided
Housing for All Delivery Pipeline 2023
No alt text provided
No. of Potential Units Per LEA
No alt text provided
image
No alt text provided
tableEx
No alt text provided

## Slide 3
LEA | Site | No. | Update
Clondalkin | Old Nangor Rd. (Simon) | 10 | Revised planning application- add info sought by planning. Response due end of Sept
 | Watery Lane (Pt V) | 6 | Part V to be agreed/ lack of meaningful engagement by developer
 | Clonburris Private (Pt V) | 100+ | On site Part V to be agreed/delivery estimated from 2024
 | St Finians Way, Newcastle | 1 | On site, Part V engagement underway, delivery 2024
 | Gordon Pk/Clondalkin Rugby Club (Pt V) | 7 | Part V to be agreed/delivery est. 2024
 | Parklands Ph1 Citywest | 23 | Part V agreed / delivery in 2024
Rathfarnham/Templeogue | Watson Place Ballyroan House | 2 | Part V to be agreed/delivery est. 2024
 | Walkinstown House, Walkinstown Roundabout | 16 | Part V to be agreed/delivery est. 2024
Firhouse/Bohernabreena | Homeville * | 16 | Approval awaited from Dept/Contractor on site/ Delivery mid-2024.
 | Pearse Brothers Park * | 10 | Tender for contractor to be advertised Q4 2023
 | Garrettstown House/Laurel Manor (Pt V) | 2 | Part V to be agreed / delivery est 2024
Tallaght Central | Former Gallaghers site (Airton/Green Rd) | 50 | Part V agreed delivery expected 2025
 | St. Aongus’ Green | 10 | Tender for contractor to be advertised Q3 2023
 | Airton Plaza (Part V) | 30 | Part V negotiations ongoing, delivery 2025
Approved/Proposed Developments by LEA (1)
Notes: * Denotes SDCC owned site

## Slide 4
LEA | Site | No. | Update
Tallaght South | Rossfield * | 16 | Planning derogation to be advertised in coming weeks
 | Citywest View (Cooldown Commons Ph3) | 36 | Part V negotiations underway, delivery Q4 2023/2024
 | Brownsbarn Citywest | 77 | Part V negotiations underway potential delivery 24 /25
 | Silken Avenue Kingswood | 1 | Part V under negotiation potential delivery Q4 23/Q1 24
 | Citywest Shopping Centre/Citywest Drive | 29 | Part V under negotiation est delivery Q4 2023/Q1 2024
Lucan | Aderrig Ph 1 | 21 | On site due for delivery 2024, part V agreed
 | Aderrig Ph 2 | 23 | On site due for delivery 2024, part V agreed
 | Tandys Lane Ph 1 (Pt V) | 24 | Part V agreed due for delivery Q4 20234
 | Tandys Lane Ph 2 (Pt V) | 35 | On site due, delivery 2024/2025
 | St Helens Plaza (Pt V) | 4 | On site-due for completion late 2024/early 2025
 | Ardeevin (Pt V) | 2 | On site due for delivery 2024
 | St Edmunds (Pt V - TAU Fonthill) | 7 | Part V agreed, on site, delivery late Dec /Jan’24
 | Adamstown Station/District Centre (Pt V) | 74 | Part V units various phases/delivery from 2024
 | Dodsborough Cottages (Pt V) | 1 | Part V agreed
 | Clonburris Private (Pt V) | 56 | Part V to be agreed/potential delivery from late 2024
Palmerstown/Fonthill | Balgaddy * | 69 | Contractor on site, delivery 2024
 | Old Lucan Rd (Túath) | 4 | SDCC investigating acquiring adjacent strip of land.
 | St. Ronan’s * | 9 | Design team appointed/Contractor tender Q4 2023 Delivery 2024
Approved/Proposed Developments by LEA (2)
Notes: * Denotes Council owned site

## Slide 5
SDCC-owned Large Sites
Kilcarbery: 1,034 homes with 30% social (310 homes)
Projected delivery of 103+ social and 29 discounted/affordable purchase homes in 2023, scope for further social homes. Developer submitting revised planning permission to add additional floor to two apartment blocks. Planning designs currently being progressed for additional 80 units social & affordable units with advertising of Part 8 derogation in late 2023.
Killinarden: 620 homes (including 125 social & 372 affordable purchase).
Planning approval received, discussions ongoing with developer in relation to cost inflation, proposal to replace private units with cost rental units. Once discussions complete developer anticipates being on site before year end, projected delivery from late 2024.
Clonburris: Phases 1 & 2 comprising 382 homes (149 social), Phases 3,4,5 with potential for 1,430* homes ( approx. 40% social)
Design Teams now appointed to deliver schemes for sites 3,4 and 5- working towards Part 10 application in 2024. Preferred tenderer identified for Clonburris Site 2, anticipates being on site in Q4 2023, build programme 24 months. Clonburris Site 1 (Kishogue) currently out to Stage 2 tender- returns due 11th October. Proposed PPP site comprising 120* social homes–Section 85 approved Feb 2023 – Part 8 to be advertised Feb 24.
Belgard Square North: 133 cost rental apartments
Contractor commenced on site April’23. Delivery estimated March 2025.
Rathcoole: Number of homes & tenure mix to be confirmed
Revised masterplan finalised which includes social, TA and scope for affordable housing to be examined and progressed.

## Slide 6: Council owned sites to be progressed in 2023 / Avail of Planning Derogation
Location | Est. No. Units | LEA | Status | Next Action | Timeline
Rossfield | 15 | Tallaght South | Planning | Advertise scheme for planning Tender to appoint contractors by end Qtr 4 | Q4 2023
Alpine Heights | 13 | Clondalkin | Feasibility Report | ACM Feb 23 Design Team appointed. Meeting held with local residents & members re: scheme | Q4 2023
Deansrath/Melrose | 24 | Clondalkin | Planning | Advertise scheme Submission to Department made for funding | Q4 2023
Kilcarbery 2 (social & affordable) | 80 | Clondalkin | Feasibility Report | Concept design to April 23 ACM | Q1 2024
Old Castle Clondalkin (social, afford, & TA) | 130 | Clondalkin | Prepare scheme for planning | ACM Dec 22/ Design being progressed for planning to avail of derogation. Consultation ongoing with residents. | Q1 2024
Castlefield (social & affordable) | 34 | Firhouse/Boherna. | Feasibility Report | ACM Feb 23/progress for planning | Q1 2024
Stocking Lane | 32 | Firhouse/Boherna. | Feasibility Report | ACM Feb 23/ progress for planning | Q1 2024
Sarsfield Park, Lucan | 5 | Lucan | Feasibility report | Concept design ACM April 23 funding submission made to Department. Scheme to be advertised Q4 2023 | Q4 2023