## Slide 1
Housing Delivery Update Report Rathfarnham Templeogue Firhouse Bohernabreena ACM
12 December 2023

## Slide 3
LEA | Site | No. | Update
Clondalkin | Old Nangor Rd. (Simon) | 10 | Planning permission refused. Appeal lodged to ABP 20/11/2023
 | Watery Lane (Pt V) | 6 | Part V negotiations ongoing
 | Clonburris Private (Pt V) | 100+ | On site. Part V to be agreed/delivery estimated from 2024
 | St Finians Way, Newcastle | 1 | On site. Part V to be agreed/delivery estimated from 2024
 | Gordon Pk/Clondalkin Rugby Club (Pt V) | 7 | Part V agreed. Delivery in 2024
 | Parklands Ph1 Citywest | 23 | Part V agreed. Delivered 2023
Rathfarnham/Templeogue | Watson Place Ballyroan House | 2 | Part V negotiations ongoing / delivery in 2024
 | Walkinstown House, Walkinstown Roundabout | 16 | Part V negotiations ongoing / delivery in 2024
Firhouse/Bohernabreena | Homeville * | 16 | Revised funding approval received from DHLGH / Contractor on site/ Delivery mid-2024.
 | Pearse Brothers Park * | 10 | Tender for contractor advertised Oct 2023. Tender assessment to be complete
 | Garrettstown House/Laurel Manor (Pt V) | 2 | Part V negotiations ongoing / delivery in 2024
Tallaght Central | Former Gallaghers site (Airton/Green Rd) | 50 | Part V agreed. Delivery expected 2025
 | St. Aongus’ Green | 10 | Tender for contractor advertised Nov 2023.
 | Airton Plaza (Part V) | 30 | On site. Part V to be agreed/delivery estimated from 2025
Approved/Proposed Developments by LEA (1)
Notes: * Denotes SDCC owned site

## Slide 4
LEA | Site | No. | Update
Tallaght South | Rossfield * | 16 | Planning derogation to be advertised December 2023
 | Citywest View (Cooldown Commons Ph3) | 36 | Part V negotiations ongoing. Delivery in 2024
 | Brownsbarn Citywest | 77 | Part V negotiations ongoing. Delivery in 2024/2025
 | Silken Avenue Kingswood | 1 | Part V negotiations ongoing. Delivery in 2024
 | Citywest Shopping Centre/Citywest Drive | 29 | Part V agreed. Delivery 2025
Lucan | Aderrig Ph 1 | 21 | Part V agreed. Delivered 2023
 | Aderrig Ph 2 | 23 | Part V agreed. Delivery 2023 / 2024
 | Tandys Lane Ph 1 (Pt V) | 24 | Part V agreed. Delivered 2023
 | Tandys Lane Ph 2 (Pt V) | 35 | On site-due for completion late 2024/ 2025
 | St Helens Plaza (Pt V) | 4 | On site-due for completion late 2024/early 2025
 | Ardeevin (Pt V) | 2 | On site due for delivery 2024
 | St Edmunds (Pt V - TAU Fonthill) | 7 | Part V agreed, on site, delivery late Dec /Jan’24
 | Adamstown Station/District Centre (Pt V) | 74 | Part V units' various phases/delivery from 2024
 | Dodsborough Cottages (Pt V) | 1 | Part V agreed
 | Clonburris Private (Pt V) | 56 | Part V to be agreed/potential delivery from late 2024
Palmerstown/Fonthill | Balgaddy * | 69 | Contractor on site. 20 units delivered 2023. Balance Q1 2024
 | Old Lucan Rd (Túath) | 4 | SDCC investigating acquiring adjacent strip of land.
 | St. Ronan’s * | 9 | Tender to be advertised December 2023.
Approved/Proposed Developments by LEA (2)
Notes: * Denotes Council owned site

## Slide 5
SDCC-owned Large Sites
Kilcarbery: 1,034 homes with 30% social (310 homes)
Construction on phase 2 of the programme is now substantially complete. Construction in phase 3 commenced in October 2023 with construction to commence on phase 4 in early 2024. A total of 103 social and 29 affordable purchase homes projected for completion in 2023. Detailed design on the adjacent site for the proposed development of 88 social and affordable homes is now complete and will be advertised shortly under the temporary Part 8 planning exemption.
Killinarden: 620 homes (including 125 social & 372 affordable purchase).
Planning approval received, discussions ongoing with developer in relation to cost inflation and a proposal to replace private units with cost rental units. Once discussions complete developer anticipates being on site in Q1 2024.
Clonburris: Phases 1 & 2 comprising 382 homes (149 social), Phases 3,4,5 with potential for 1,430* homes ( approx. 40% social)
Construction has commenced onsite in the Canal Extension sector on 116 social and affordable homes. The final stage of the tender process for construction of 266 social, affordable, and cost rental homes in the Kishogue sector is currently paused to resolve technical design issues. Design work is progressing for approximately 120 social homes on the PPP site adjacent to Lynches Park. This scheme is expected to go to Part 8 public consultation in February 2024. Design is also ongoing for phases 3,4 & 5 with a planning application to An Bord Pleanala planned for mid 2024.
Belgard Square North: 133 cost rental apartments
Contractor commenced on site April’23. Delivery estimated March 2025.
Rathcoole: Number of homes & tenure mix to be confirmed
Design work to incorporate the proposed housing, school, and sports facilities is ongoing. An update will issue to local Councillors ahead of finalising a planning application

## Slide 6: Council owned sites to be progressed in 2023 / Avail of Planning Derogation
Location | Est. No. Units | LEA | Status | Next Action | Timeline
Rossfield | 16 | Tallaght South | Planning | Scheme advertised in December 2023. Tender to be advertised. | Q1 2024
Alpine Heights | 13 | Clondalkin | Design | Design almost complete. Update to be provided to residents directly adjoining site. | Q1 2024
Deansrath/Melrose | 24 | Clondalkin | Planning | Scheme advertised in December 2023. Tender to be advertised. Stage 1 funding application approved by DHLGH Sept 2023 | Q2 2024
Kilcarbery 2 (social & affordable) | 88 | Clondalkin | Design | Scheme to be advertised in Dec 2023. | Q3 2024
Old Castle Clondalkin (social, afford, & TA) | 130 | Clondalkin | Prepare scheme for planning | Design being progressed for planning to avail of derogation. Consultation ongoing with residents. | Q3 2024
Castlefield (social & affordable) | 33 | Firhouse/Boherna. | Design | In house design. Detailed design ongoing. | Q2 2024
Stocking Lane | 32 | Firhouse/Boherna. | Feasibility Report | Progress for planning advertising | Q1 2024
Sarsfield Park, Lucan | 5 | Lucan | Planning | Scheme to be advertised in Dec 2023. DHLGH Funding approved Nov 2023. | Q2 2024