## Slide 1
Traveller Accommodation Programme (TAP)
2025-2029

## Slide 2: Key Dates and Implementation of TAP (2025-2029)
Date | Summary of Action
January 2024 | One months’ notice given to adjoining local authorities, HSE, LTACC, Local Traveller Development Groups, AHB’s and Community bodies
February 2024 | Closing Date for submissions
Feb/Mar 2024 | Conduct Needs Assessment - Existing and projected accommodation needs Types of accommodation required
Mar/Apr 2024 | Analysis of results of assessment of need
May/June 2024 | Preparation of Draft Traveller Accommodation Programme to include - Summary Form showing needs for all categories of Traveller accommodation Policy statement and strategy Measures to implement the programme
1st July 2024 | Publish notice in newspapers- Draft programme displayed and made available for inspection & circulated to all stakeholders

## Slide 3: Key Dates and Implementation of TAP (2025-2029)
Date | Summary of Action
30th Aug 2024 | Latest date for receipt of written submissions on draft programme
1st Oct 2024 | Submission of draft programme to Elected members for adoption
31st Dec 2024 | Latest date for adoption of programme
21st Jan 2025 | Latest date for adjournment of council meetings
21st Feb 2025 | If failure to adopt by Elected members, a further 1 month is allowed before the programme, as may be modified, is adopted by Chief Executive Order
Following adoption | Publication and submission to the Minister of adopted programme Will be reviewed at least once during lifetime of the programme

## Slide 4: Progress to Date (TAP 2025-2029)
Date | Summary of Action
January 2024 | Notice given of the Preparation of the Draft Traveller Accommodation Programme 2025-29 to adjoining local authorities, HSE, LTACC, Local Traveller Development Groups, AHB’s, including CENA and Community bodies
8th February 2024 | Closing Date for submissions
February 2024 | Commencement of Assessment of Need

## Slide 5: Assessment of Need
Summary of Actions to be completed:
Estimate of accommodation needs of Travellers living in South Dublin during TAP 2025 – 2029: To be determined: Existing needs Projected needs
The Assessment of Need must have taken into account the preferred options as outlined in the Summary of Social Housing Assessments, including housing options below: Standard Local Authority Housing Approved Housing Body Housing Traveller Specific accommodation – group housing schemes and halting sites Private Rented Accommodation Need for Transient sites

## Slide 6: TAP 2025 to 2029 Assessment of Needs

## Slide 7: 2025 to 2029 TAP Project Management Chart

## Slide 8
Consultation with the LTACC is key
Involved at each step from Notice of Assessment of Needs to preparation of Draft Programme and Adoption of Programme
Facilitate consultation between Local Authority and members of the Traveller Community in South Dublin Administrative Area
Advise on any aspect of accommodation for members of the Traveller Community in South Dublin
Notes: Give CC and Comms figures for Emma, talk of how our county is the most engaged on social media during events like this