COMHAIRLE CHONTAE ÁTHA CLIATH THEAS

SOUTH DUBLIN COUNTY COUNCIL

# MEETING OF TALLAGHT AREA COMMITTEE (1)

MONDAY 19th JUNE  2006

H I – 6

## Report on Housing Construction Programme:

The up-to-date position of the construction programme for the County area is set out in the detail below: -

Completions in 2004:-

| Total | No. of Units | 81 |
| --- | --- | --- |

Completions in 2005:-

| Scheme Name | No. of Units | Completion Dates |
| --- | --- | --- |
| Russell Square | 110 | 2005 |
| Bawnlea | 7 | March 2005 |
| Jobstown Village Core | 10 | March 2005 |
| Cushlawn, Phase II | 31 | 2005 |
| Daletree, Ballycragh | 8 | September 2005 |
| Fettercairn Village | 22 | 2005 |
| Sub Total | 188 |  |

Completions in 2006:-

| Total | No. of Units | Completion Dates |
| --- | --- | --- |
| Fettercairn Village | 9 | February 2006 |
| Fettercairn Village | 9 | May 2006 |
| Deerpark (Joint Venture) | 11 | May 2006 |
| Sub Total | 29 |  |

### On Site:-

| Scheme Name | No. of Units on Site | Completion Dates |
| --- | --- | --- |
| Avonbeg, Phase 3 | 47 | In phases end September, 2006 |
| Fortunestown B, Phase 2 | 66 (+52 Vol. Units) | Early July 2006 |
| Fortunestown B, Phase 4 | 120 | July, 2006 |
| Fortunestown B, Phase 1 | 110 | In phases from December 2006 |
| Deerpark (Joint Venture) | 108 | (In phases) May 2006 |
| Daletree (Part 5/Joint Venture) | 27 | (in phases) October 2005 |
| Hunterswood (Part V) | 9 | Late 2006 |
| Brookfield Village+ Community Facility | 16 | September 2006 |
| Deerpark (Part V) | 36 | From May 2006 (in phases) |
| Belfry | 35 | December 2006 |
| Belgard Square | 44 | Late 2006 |
| Castlepark | 9 | July 2007 |
| Cushlawn Phase 3 | 22 | December 2007 |
| Sub.Total | 649 |  |

Tenders Recommended

| Scheme Name | No of Units |
| --- | --- |
| Kilcarrig Phase 3 (SH274) | Tender approval in the sum of €13,694,694 received from the DoEHLG for approval for the construction of 80 units by D&I Construction Ltd., Tyrell House, Main Street Blessington, Co Wicklow |
| Sub Total | 80 |

Tender Production

| Scheme Name | No. of Housing Units |
| --- | --- |
| Kiltalown Green | 28 |
| Sub Total | 28 |

Part 8 Approved by Council:-

| Scheme Name | No. of Housing Units |
| --- | --- |
| Avonbeg Phase 4 (SH252) | 7 & St Muirins House – Cost Plan submitted to the DoEHLG for approval on 07/11/2005 |
| Sub Total | 7 |

Part 8 Advertised:-

| ### Scheme Name | ### Approx. No. Of Units |
| --- | --- |
| ### Fortunestown B, Phase3 & 5 | ### 160 |
| ### Fettercairn Phase 2 | ### 33 |
| ### TOTAL | 193 |

Part 8 – plans on display

| Scheme Name | No of units | Comprising | On display until | Closing date for submissions and observations |
| --- | --- | --- | --- | --- |
| ### Knockmore House (incl. 15 units for Bernardos) | ### 84 | 12 no. 2/3 bedroom units, 7 no. two storey two bedroom units; 26 no. one and a half storey/two storey units; 26 no. three storey three bedroom units; 9 no. two storey three bedroom houses and 4 no. own door two bedroom apartments | 12th June 2006 | 26th June 2006 |
| ### Rossfield Infill | 9 plus commercial units | 2 no. two bedroom own-door apartments and 3 no. three bedroom duplex units over, on site fronting onto Brookfield Avenue. 2 no. own-door one bedroom apartments with 2 no. three bedroom duplex units | 12th June 2006 | 26th June 2006 |
| ### Castletymon | 67 | 29 number five person two storey units in terrace format, 24 number three person own door apartment units in eight individual three storey blocks at corner locations; and 14 number four person two storey units in terrace format. | 15th June 2006 | 29th June 2006 |

At Concept/Design Stage:-

| ### Scheme Name | ### Approx . No. Of Units |
| --- | --- |
| ### Kilclare, Phase2 | ### 30 (concepts presented to Tallaght Area Committee Meeting 16/06//2003) |
| ### Kilclare Phase3 | ### 15 units |
| Whitestown Stream | 177 private/affordable/social/ voluntary units |
| Suncroft | 10 units |
| Whitebrook Park | 25 units - (concepts presented to Tallaght Area Committee Meeting 20/09/2004) – land transfer to be finalised by development department |
| ### Stocking Lane | - (concept under preparation) |
| ### Swiftbrook | 11 units -(concept presented to Tallaght Area Committee Meeting 08/12/04) |
| ### Sub Total | 268 |

Other potential sites are also being examined.