## Slide 1
Housing Delivery Update Report Rathfarnham Templeogue Firhouse Bohernabreena Area Committee Meeting 12th March 2024

## Slide 2
Target 2023
Housing for All – Delivered 2023
Delivery Stream
Delivery by LEA
Clondalkin
Tallaght-Central

## Slide 4: Housing Developments Approved / Under Construction – Rathfarnham / Templeogue/ Firhouse/ Bohernabreena
L.E.A | Project | Delivery | Units | Status
Rathfarnham/ Templeogue | Walkinstown House | Part V | 16 | Part V Agreed – Delivery 2025
 | Nutgrove Avenue | Part V | 3 | Negotiations to commence. Delivery 2025
Firhouse/ Bohernabreena | Homeville | LA Build | 16 | On site. Due for delivery Q3 2024
 | Pearse Brothers Park | LA Build | 10 | Contract awarded. Commencement on site Q1 2024
 | Laurel Manor | Part V | 2 | On site due for delivery 2024.

## Slide 5
Large Development Sites
Kilcarbery: 1,034 homes with 30% social (310 homes)
Delivery of 74 social homes anticipated in 2024. Design work is continuing for the adjacent site with a proposed development of up to 88 social and affordable homes.
Killinarden Foothills: 620 homes (including 125 social , 123 Private & 372 affordable purchase).
Developer is currently completed pre-construction planning compliances and with a view to commencing works onsite.
Clonburris: Phases 1 & 2 comprising 382 homes (149 social), Phases 3,4,5 with potential for 1,430* homes ( approx. 40% social)
Construction continuing on-site Canal Extension. The tender process for construction of 266 social, affordable, and cost rental homes in the Kishogue sector has recommenced. Anticipated on-site date in Q3 2024, to allow for completion of road construction works. Design work is almost complete for 120 social homes on the PPP site adjacent to Lynch’s Park, with Part 8 due to commence once complete. Plans for approximately 1300 social and affordable homes are currently being advanced by external design teams with a Part 10 planning application to An Bord Pleanála expected in Summer 2024.
Belgard Square North: 133 cost rental apartments
Contractor commenced on site April’23. Delivery March 2025 .
Rathcoole: Number of homes & tenure mix to be confirmed
Due to commence procurement process to appoint consultant to progress the masterplan through to Part 10 planning application application to An Bord Pleanála.

## Slide 6: Planning Derogation Sites - ( Section 179A)
Location | Units | LEA | Status | Next Action
Rossfield | 16 | Tallaght South | Planning | Scheme advertised in December 2023. Tender to be advertised in Q1 2024
Alpine Heights | 13 | Clondalkin | Detailed Design | Final design complete. Architects to meet with residents prior to advertising of scheme.
Deansrath/Melrose | 24 | Clondalkin | Planning | Scheme advertised in December 2023. Tender to be advertised in Q1 2024
Kilcarbery 2 (Social & affordable) | 88 | Clondalkin | Detailed Design | Scheme advertised in December 2023. Procurement process to be commenced shortly
Old Castle Clondalkin ( Social, affordable, & TA) | 130 | Clondalkin | Detailed Design | Consultation with residents ongoing. Design to be finalised.
Castlefield (Social & affordable) | 33 | Firhouse/Bohernabreena | Detailed Design | In house design. Detailed design ongoing
Stocking Lane | 25 | Firhouse/Bohernabreena | Feasibility Report | Progress for planning advertising
Sarsfield Park, Lucan | 5 | Lucan | Planning | DHLGH Funding approved Nov 2023

## Slide 7
Tenant in Situ Acquisitions