## Slide 1
Traveller Accommodation Programme (TAP)
2025-2029

## Slide 2: Progress to Date of TAP (2025-2029)
Date | Summary of Action
January 2024 | One months’ notice given to adjoining local authorities, HSE, LTACC, Local Traveller Development Groups, AHB’s and Community bodies
February 2024 | Closing Date for submissions
Feb/Mar 2024 | Conduct Needs Assessment - Existing and projected accommodation needs Types of accommodation required
Mar/Apr 2024 | Analysis of results of assessment of need Preparation for Focus Groups

## Slide 3: Key Dates and Implementation of TAP (2025-2029)
Date | Summary of Action
January 2024 | One months’ notice given to adjoining local authorities, HSE, LTACC, Local Traveller Development Groups, AHB’s and Community bodies
February 2024 | Closing Date for submissions
Feb/Mar 2024 | Conduct Needs Assessment - Existing and projected accommodation needs Types of accommodation required
Mar/Apr 2024 | Analysis of results of assessment of need Facilitation of 3 Focus Groups
May/June 2024 | Preparation of Draft Traveller Accommodation Programme to include - Summary Form showing needs for all categories of Traveller accommodation Policy statement and strategy Measures to implement the programme
1st July 2024 | Publish notice in newspapers- Draft programme displayed and made available for inspection & circulated to all stakeholders

## Slide 4: Key Dates and Implementation of TAP (2025-2029)
Date | Summary of Action
30th Aug 2024 | Latest date for receipt of written submissions on draft programme
1st Oct 2024 | Submission of draft programme to Elected members for adoption
31st Dec 2024 | Latest date for adoption of programme
21st Jan 2025 | Latest date for adjournment of council meetings
21st Feb 2025 | If failure to adopt by Elected members, a further 1 month is allowed before the programme, as may be modified, is adopted by Chief Executive Order
Following adoption | Publication and submission to the Minister of adopted programme Will be reviewed at least once during lifetime of the programme

## Slide 5: Assessment of Need TAP 2025 - 2029
Actions to date
Assessment of Needs commenced on 27th February 2024:
Summary - households surveyed to date: 8 households (5.5%) refused to engage. 50 households - uncontactable– follow up attempts being made to revisit. Findings to date: 92 Adults currently residing with family members – 56 adults expressed an interest in Standard Housing only. 31 adults in Group Housing Schemes with 5 adults preferring to be housed in Halting Site Accommodation only. 28 teenagers within the 16- to 18-year-old in total – 17 expressing an interest in Standard housing, 8 in Group Housing Schemes and 3 Halting Sites. 0 expression of preference in Transient Sites Focus Groups commencing 17th April in Clondalkin Travellers CDP – Tallaght dates to be confirmed.

## Slide 6: 2025 to 2029 TAP Project Management Chart

## Slide 7: TAP 2025 to 2029 Assessment of Needs