SOUTH DUBLIN COUNTY COUNCIL

COMHAIRLE CHONTAE ÁTHA CLIATH THEAS

# MEETING OF TALLAGHT AREA COMMITTEE (1)

Monday 19th June 2006

Headed Item HI-8

Six-Monthly Report on Implementation of Timetable of Programmes and Services in the West Tallaght Area (following from motion adopted at Council Meeting of 9th May 2005 at which the Traveller Accommodation Programme 2005-2008 was adopted)

The Council, at its Special Adjourned Meeting held on 9th May 2005, adopted the Traveller Accommodation Programme 2005-2008. During the course of the meeting the following motion was tabled by Councillor C. Jones and seconded by Councillor Eamonn Walsh:

“That this Council in the provision of a Group Housing scheme for Fortunestown ‘B’ commits to achieving the urgent essential services for the people of West Tallaght supports the implementation of a timetable, concluding December 2007.  This timetable to include:

- The provision of a comprehensive social integration programme within local schools

- Provision of additional crèche and playground facilities

- The sustainable operation of the existing all-weather pitches

- The sustainable operation of the local Swimming Pool

- The upgrading of St. Aidan’s Halting Site

- The sustainable operation of the Brookfield Community & Youth Facility.

This timetable to be subject to a six-monthly report to the Tallaght Area Committee commencing June 2005.”

Following discussion the motion was passed.

## Group Housing Scheme at Fortunestown

A report on Public Notification procedure under Part 8 of the Planning and Development Regulations 2001- 2003 for the proposed construction of Traveller-specific accommodation comprising ten group houses and all necessary associated ancillary works on a site at Fortunestown, Tallaght, Dublin 24 was noted by the Council at its meeting on 11th July 2005.

Construction of the ten group houses is ongoing and work is scheduled to be completed later this year.

## Schools Programme

Prior to 9th May 2005 there had been a series of meetings with the Principal of St. Aidan’s Community School. The programmes that operate within the school already are impressive and include breakfast clubs, homework clubs, the School Completion Programme and indeed the school was the first in Dublin (second nationally) to introduce the Discipline for Learning Programme a number of years ago.

Further discussions have taken place between the Council, the Department of Education & Science and St. Aidan’s Community school with regard to developing a detailed proposal on the creation of an e-learning project which will enhance educational achievement among new school entrants.

Teachers in the school have been issued with laptops and have undergone necessary training.

An e-champion to assist staff in the school is currently being recruited.

Crèche and Playground facilities

The provision of these facilities is reported in detail in the West Tallaght Study and its associated updates. The report also includes details of the additional crèche and playground facilities which are being provided in the area as part of the overall development of the area.

Childcare facilities have already been provided in Jobstown and in a number of the private developments constructed in the area on foot of planning permissions. A site has been reserved and a design approved for an additional childcare facility in Brookfield adjacent to the Community / Youth facility at present under construction. An application for funding for this project is at present being finalised. A site has also been reserved and a design is at Part 8 approval stage for the childcare facility in Fortunestown. A report on the completion of the Part 8 process at present underway will be made to the next meeting of the Council. When approved the construction of this childcare facility will be incorporated as an integral element of the construction tender and will be constructed as part of the overall scheme.

The provision of playground facilities was also an integral element of the West Tallaght Study. One of the required facilities is being provided as an integral element of the Community / Youth facility which is under construction at present. Another playground facility is also included in the current Part 8 process for Fortunestown which will the subject of a report to next month’s Council meeting. As with the childcare facility, the playground facility will be incorporated as an integral element of the construction tender and will be constructed as part of the overall scheme. The current Part 8 also makes provision for the construction of a community café and additional community rooms.

## All Weather Pitches

The Council is represented on the Board which oversees the management of the Jobstown all weather pitches. The pitches are managed by Jobstown All Weather Pitch Ltd. The operation of the pitches is satisfactory. The Council will continue to be involved in this project.

## Swimming Pool

The swimming pool and sports hall development is progressing well and is expected to be completed by September 2006. A management company to provide services to the facility has been approved and heads of agreements are in place.

The management company will launch a campaign (involving school visits, information days, etc.) to inform residents in the area about the facility in August.

## St. Aidan’s Residential Caravan Park

## As previously agreed, it is proposed in conjunction with the construction of the five group houses, to carry out upgrading / refurbishment works to the existing residential caravan park.

The initial proposal was to address the environmental upgrade of the area to the front of the existing site and was to be designed in a manner so as to integrate the existing developments with the new developments. The existing residential caravan site was substantially upgraded a number of years ago including the upgrading of the community facilities on site and the provision of an indoor area for games such as handball and boxing. The area to the west of the site entrance has been upgraded to include a newly planted landscaped area in order to integrate the new Group Housing with the existing development and the existing caretaker’s house.

The carrying out of further upgrading / refurbishment works to the area to the east of existing residential caravan park has been deferred pending a review of the use of the existing community and sports facilities on site being carried out in conjunction with the Tallaght Travellers Services – St Aidans Traveller Centre Tallaght. Following a recent meeting with the Project Team, certain further additional information has been requested. On receipt of their reply a final decision on the matter will be made.

## Brookfield Community and Youth Facility

As outlined in the last report to the Area Committee, the facility is on schedule and it is anticipated that it will be completed in October of this year.

The re-furbishment of the existing Brookfield Community Centre is complete and the centre is now fully operational.