## Slide 1
Housing Delivery Report Lucan / Palmerstown / North Clondalkin
Area Committee Meeting 23rd April 2024

## Slide 3: Housing Developments Approved / Under Construction – Lucan / Palmerstown / North Clondalkin
L.E.A | Project | Delivery | Units | Status
Lucan | Aderrig, Phase 2 | Part V | 23 | Part V agreed. All units to be delivered in Q2 & Q3.2024
 | Tandy's Lane Ph 2 | Part V | 15 | On site due, delivery Q4 2024 & Q2.2025
 | St Helens Plaza | Part V | 80 | On site due for completion early 2026
 | Adamstown Station/District Centre | Part V | 74 | On site due for delivery Q3 & Q4.2024.
 | Tandy’s Lane | LA Acquisition | 3 | Delivery Q2.2024
 | Adamstown Boulevard | Part V | 26 | Part V agreed. Delivery 2025 & 2026
 | Ardeevin | Part V | 2 | Part V in negotiation. Delivery 2025
Palmerstown/ Fonthill | Balgaddy | LA Build | 69 | Construction on-going. Delivery of balance of 49 units in Q2.2024
 | St. Ronan’s Crescent (Age Friendly) | LA Build | 9 | Tender under evaluation

## Slide 4
Large Development Sites
Kilcarbery: 1,034 homes with 30% social (310 homes)
Phase 1 & 2 of this project is now complete. Construction work is continuing through phases 3 & 4. Delivery of 74 social homes anticipated in 2024. 21 social homes to be delivered w/e 19/04/2024. Design work is almost complete for the adjacent site with a proposed development of up to 88 social and affordable homes. The next stage is to proceed to procurement.
Killinarden Foothills: 620 homes (including 125 social , 123 Private & 372 affordable purchase).
Developer is currently completed pre-construction planning compliances and with a view to commencing works onsite in the coming weeks.
Clonburris: Phases 1 & 2 comprising 382 homes (149 social), Phases 3,4,5 with potential for 1,430* homes ( approx. 40% social)
Construction continuing on-site Canal Extension. The tender process for construction of 266 social, affordable, and cost rental homes in the Kishogue sector has recommenced. Anticipated on-site date in Q3 2024, to allow for completion of road construction works. Design work is almost complete for 120 social homes on the PPP site adjacent to Lynch’s Park, with Part 8 due to commence once complete. Plans for approximately 1300 social and affordable homes are currently being advanced by external design teams with a Part 10 planning application to An Bord Pleanála expected in Summer 2024.
Belgard Square North: 133 cost rental apartments
Contractor commenced on site April 2023. Delivery March 2025 .
Rathcoole: Number of homes & tenure mix to be confirmed
Due to commence procurement process to appoint consultant to progress the masterplan through to Part 10 planning application application to An Bord Pleanála.

## Slide 5: Planning Derogation Sites - ( Section 179A)
Location | Units | LEA | Status | Next Action
Rossfield | 16 | Tallaght South | Planning | Scheme advertised in December 2023. Tender to be advertised in Q2 2024
Alpine Heights | 13 | Clondalkin | Planning | Final design complete. Scheme currently on advertisement until 30.05.2024. Following this we will proceed to tender advertisement.
Deansrath/Melrose | 24 | Clondalkin | Planning | Scheme advertised in December 2023. Tender to be advertised in Q2 2024
Kilcarbery 2 (Social & affordable) | 88 | Clondalkin | Planning | Scheme advertised in December 2023. Procurement process to be commenced shortly
Old Castle Clondalkin ( Social, affordable, & TA) | 130 | Clondalkin | Detailed Design | Consultation with residents ongoing. Design to be finalised.
Castlefield (Social & affordable) | 33 | Firhouse/Bohernabreena | Planning | Design work complete. Will progress to relevant AA and EIA Screenings and will advertise in June 2024
Stocking Lane | 25 | Firhouse/Bohernabreena | Feasibility Report | Progress for planning advertising
Sarsfield Park, Lucan | 5 | Lucan | Planning | Design complete. Currently on advertisement until 06.06.2024

## Slide 6
Tenant in Situ Acquisitions

## Slide 7
56
Delivered