## Spend Breakdown
Spend Breakdown
300K Area | Total Monies Spent | Total Monies still Committed | Total Monies Unspent
Lucan | 260000 | 20000 | 10000
Clondalkin | 157700 | 40000 | 105000
Firhouse Bohernabreena | 150000 | 140000 | 0
Tallaght Central | 157000 | 80000 | 60000
Rathfarnham Templeogue | 132000 | 165000 | 0
Tallaght South & Saggart |  | 295500
TOTAL | 856700 | 740500 | 175000

## 2017 Lucan
LUCAN
Project | Votes Cast | Funding Amount | Status
Playground in Waterstown Park, Palmerstown | 1184 | 120000 | Complete
Feasibility Study for the Restoration of Silver Bridge, Palmerstown | 1148 | 15000 | Complete
Christmas Lights in Lucan Village | 1076 | 17000 | Complete
Planting Native Apple Trees, Lucan Electoral Area | 935 | 5000 | Complete
Access to Church and Graveyard at Mill Lane, Palmerstown | 869 | 10000 | Not Complete - this has stalled due to local issues with the access point and the church can be accessed from the park
Free Library Book Banks in Public Places - Lucan Electoral Area | 865 | 3000 | Complete
Multi-Games Wall in Lucan | 860 | 100000 | Complete
Restoration of King John’s Bridge Griffeen Park - Lucan | 806 | 20000 | Ongoing - money still committed to carry out work
Total |  | 290000
Total monies spent | 260000
Total Monies still committed | 20000
Total Monies unspent | 10000

## 2018 - Clondalkin
CLONDALKIN
Project | Votes Cast | Funding Amount | Status
Pedestrian Link between the Round Tower and Corkagh Park | 567 | 40000 | Paused - funding allocated not sufficient upon initial research. It is the intention to deliver under the Corkagh to Grand Canal (via Clodalkin) under the Active Travel Scheme. NTA funded scheme has been initiated. Awaiting further developments
Renovate Portocabin for the Clondalkin Men Shed | 556 | 7000 | Complete
Restoration of Old Nangor Road Water Pump | 518 | 1000 | Complete
New Christmas Lights for Clondalkin Village | 511 | 20000 | Complete
A Community Orchard, Clondalkin Electoral Area | 483 | 10000 | Complete
Irish Signs for Clondalkin | 474 | 3200 | Completed - in line with heritage app
Planting Flowers across the Bawnogue Area | 418 | 5000 | Complete
Safety and Inclusivity Study of Clondalkin's Public Spaces | 417 | 50000 | Complete
On-Street Bicycle Pump, Clondalkin Villlage | 395 | 3500 | Complete
Bottle banks and recycling facilities for Cherrywood | 364 | 20000 | Not Complete - resistance to the proposed location by locals, no agreed location available
WiFi Activated Self-Guided Historical Trail of Clondalkin | 357 | 30000 | Complete
New Play Ground, Forest Hill Estate | 351 | 60000 | Not Complete - consulted with the local residence association. There was a lack of support from local residents for this proposal.
Acoustic Piano for the Rathcoole Community Centre | 347 | 5000 | Not Complete -community centre have resisted and do not want it in place - construction was ongoing at community centre which paused plans - funding not drawn down as of yet and is still available to draw down
Gym Equipment and Activities for Rathcoole Community Centre | 345 | 25000 | Complete
Welcome to Clondalkin Hedge Signage | 343 | 20000 | Not Complete - The project was “to construct a ‘Welcome to Clondalkin’ greeting at Newlands Cross. This will be a mound with the words made with shrubs, such as box hedging, to provide a warm welcome to those entering Clondalkin”. Based on examination of a similar ‘hedge signs’, the dimension of the hedge would need to be approximately 15 metres long x 5 metres high. All grass verges on Fonthill Road between Boot Road and the N7 were examined for suitability. The largest area available was on the north east side of the Fonthill Road/N7 junction near the 1916 garden. This site is on the outbound side of the Fonthill Road as you exit Clondalkin. A hedge on this site would not have been visible to Clondalkin inbound traffic and was therefore unsuitable. Other locations examined were at the back/side of Newlands Cross Garden Centre and the area between the Circle K and St Brigid’s Well. Neither site had sufficient space available. There were no other locations of sufficient size to accommodate the hedge in the area examined.
Total |  | 299700
Total monies spent | 154700
Total Monies still committed | 40000
Total Monies unspent | 105000

## 2019 - Fir.BB
Firhouse - Bohernabreena
Project | Votes Cast | Funding Amount | Status
Health and Wellbeing Garden in Firhouse Community Centre | 1519 | 100000 | Works have been completed with Funding contributing to the firhouse community centre garden
Intergenerational Outdoor Activity Spaces in Glenasmole | 1472 | 140000 | Partial draw down for project already happened. Final works to be completed before remainder can be actioned. Approx 37k drawn down. €104,627.72 left to be drawn down
Nature Trail along the river Dodder | 926 | 20000 | Complete
Playground Facilities at Ballycragh Park | 782 | 20000 | Complete - Extension complete Q3 2022
Native Tree Trail in Woodlawn Park | 767 | 10000 | Complete
Total |  | 290000
Total monies spent | 150000
Total Monies still committed | 140000
Total Monies unspent | 0

## 2020&2021 - Tallaght Central
TALLAGHT CENTRAL
Project | Votes Cast | Funding Amount | Status
Sensory garden / accessible playground | 727 | 20000 | Complete
Improve the Kingswood playground | 607 | 30000 | Complete
Native tree trail in Sean Walsh Park | 528 | 10000 | Currently underway to be finalised in Q4 planting season
Signage for viewing points of the Dublin Mountains | 522 | 5000 | Construction works (Older Persons Homes) finished recently in the vicinity of the likely location for such signage in Sean Walsh Park. The department will begin discussions with the Public Realm section in order further this proposal now.
Upgrade the playground at Aylesbury Field | 511 | 40000 | Completed
Fruit Trees along Bolbrook Stream and Avonmore Road | 503 | 5000 | Completed
Basketball and tennis court in Kilnamanagh | 501 | 60000 | Local Community Groups have rejected the winning project. Submission was not made by a community group. Funding remains unused and project cannot progress. Funds remain available to be used on this project
Outdoor event space in Sean Walsh Park | 499 | 35000 | In design phase of the project having viewed and assessed canopies and other event spaces in DLR & DCC.
Toddler specific playground for Old Bawn | 476 | 30000 | Completed Dec 22
Upgrade the playground at Sean Walsh Park | 471 | 50000 | Completed - Jan 23
Signage for Tallaght waterway | 458 | 10000 | Currently in Initial planning stages within the department
A book of short stories and poetry | 325 | 2000 | Completed
Total |  | 297000
Total monies spent | 177000
Total Monies still committed | 60000
Total Monies unspent | 60000

## 2022 - Rath.Temp
RATHFARNHAM TEMPLEOGUE
Project | Votes Cast | Funding Amount | Status
A nature trail in Rathfarnham Castle Park | 1214 | 30000 | Project was expected to be in the ground during the summer months and is nearing completion
Planting fruit trees throughout the Rathfarnham Templeogue electoral area | 1208 | 20000 | Complete, trees planted in St. Annes, Greenhills Park, Moyville and Green Trees Park
Green laneways for Rathfarnham | 1165 | 10000 | Completed - reply sent to submitter - moneys have been allocated to a separate laneway following local consultation to adapt the project
Christmas lights for Templeogue Village and Rathfarnham Village | 1115 | 70000 | Lights were supplied for Rathfarnham late Dec 2023. Templeogue to arrange lights for 2023. Money still with corporate. Expecting draw downs for payment to happen early 2023 - split agreed by parties 40k Rath - 30k Temple (updated 30.1.23)
Outdoor nature classrooms on local greens | 1085 | 25000 | To be programmed for delivery following design and procurement
A bicycle pump for Templeogue Village | 952 | 5000 | Completed - SEPT 22
Run a STEAM (Science, Technology, Engineering, Arts, Mathematics) Project for children from the Traveller Community | 811 | 5000 | STEAM projects currently underway, being delivered on: April 25th, May 9th, May 16th, May 23rd, May 30th
Drinking water stations for Rathfarnham | 737 | 50000 | Contract in place. Due for delivery.
Place QR code stands near Templeogue Cemetery and the nearby Old Church | 656 | 10000 | County Promotion Unit recently launched Templeogue area on the Heritage App which has been launched in Clondalkin, Tallaght and Rathfarnham with the rest of County to follow suit.
Run a poetry competition in Rathfarnham | 440 | 2000 | The poetry competition will be run in March/April to coincide with World Poetry Day and Poetry Day Ireland
New seating for the Crannagh Road area | 358 | 10000 | Completed
Playground and seating for the College Drive/Fortfield Road | 313 | 60000 | Currently in Procurement and awaiting a contractor to carry out the work.
Total |  | 297000
Total monies spent | 132000
Total Monies still committed | 165000
Total Monies unspent | 0

## 2023 - Tallaght South & Saggart
Tallaght South and Saggart
Project | Votes Cast | Funding Amount | Status
Solar Panels on Killinarden Community Centre and CARP Killinarden | 832 | 70000 | In progress with directorate and community centre to agree installation
Foraging and land-based skills workshops in parks | 824 | 3000 | Currently being planned and delivered through our library service
Community Wellbeing Garden at Killinarden Community Centre | 800 | 100000 | In progress with directorate and community centre to agree installation
Bicycle Repair Station Next to the Saggart Luas Stop | 710 | 5000 | Complete
Christmas Lights for Saggart Village | 649 | 15000 | Complete
Heritage Trail App for Saggart Village | 579 | 12500 | County Promotion Unit recently launched Templeogue area on the Heritage App which has been launched in Clondalkin, Tallaght and Rathfarnham with the rest of County to follow suit including Saggart
New Park Benches in Carrigmore Park | 554 | 15000 | In progress - due to completed imminently
A Public Drinking Water Pump in Saggart Village | 546 | 25000 | Complete
Native Tree Trail in Carrigmore Park, Citywest | 542 | 30000 | In progress - next planting season begins in November
Mens Shed upgrade at the Fettercairn Youth and Community Centre | 469 | 20000 | In progress with directorate and community centre to agree delivery.
Total |  | 295500
Total monies spent | 45000
Total Monies still committed | 250500
Total Monies unspent | 0