## Slide 1
Social Housing Delivery
Clondalkin Newcastle Rathcoole Saggart ACM
20th November 2024

## Slide 3
Large Development Sites
Kilcarbery Grange: 1,034 homes with 30% social (310 homes)
Phase 1 & 2 of this project is now complete, with delivery of 227 social homes to date. Construction work is continuing through phases 3 & 4. Full completion of project is anticipated by mid 2025.
Clonburris: Phases 1 & 2 comprising 382 homes (149 social), Phases 3,4,5 with potential for 1,300 homes
The tender process for construction of 266 social, affordable, and cost rental homes in the Kishoge is due to close on 22nd November 2024. Anticipated on-site date in Q1 2025. Part 8 report for 118 social homes on PPP site adjacent to Lynch’s Lane went to full Council on Monday 11th November and was approved to proceed. Draft plans for approximately 1300 social and affordable homes were also presented to the Council and were noted ahead of the Part 10 application which will be submitted to An Bord Pleanála in early 2025
Rathcoole: Number of homes & tenure mix to be confirmed
Currently out for procurement for an Architect led design team to progress the masterplan through to Part 10 planning application application to An Bord Pleanála.
Kilcarbery Grange, Clondalkin
Clonburris – Stage 3 - 5

## Slide 4
Own Build Developments
LEA | Project | Units | Status
Clondalkin | Old Nangor Road (Eircom) | 93 | On-site – completion Q4.2024
 | Lindisfarne | 19 | On-site – completion Q4.2024
 | Canal Bank Extension | 56 | On-site – phased delivery from mid 2025. Mixed Tenure Scheme
 | St Ronan’s Crescent (Age-Friendly) | 9 | Tender process complete. Contractor to be appointed
 | Alpine Heights (Age-Friendly) | 13 | Tender currently advertised
 | Deansrath – Melrose | 27 | Tender currently advertised
 | Kilcarbery Phase 5 | 18 | Section 183 Disposal to Adwood approved at Council Meeting in October. On site by December 2024
Old Nangor Road,
Clondalkin
Old Nangor Road,
Clondalkin

## Slide 5
Planning Derogation Sites – Section 179A
Rossfield Avenue, Tallaght
16 Social Homes
Deansrath & Melrose, Clondalkin
27 Age-Friendly Social Homes
Kilcarbery Grange, Clondalkin
88 Social and Affordable Homes
Alpine Heights, Clondalkin
13 Age-Friendly Social Homes
Sarsfield Park, Lucan
5 Age-Friendly Social Homes
Advertised 11/04/2024. Tender advertised August 2024
Castlefield, Old Knocklyon Road
33 Social and Affordable Homes
Old Castle, Clondalkin
130 Social, Affordable and Traveller Accommodation Units
Stocking Lane, Rathfarnham
25 Social Homes
Owendoher Haven, Rathfarnham
9 Traveller Accommodation Units
FRA Ongoing
Kishogue Park, Clonburris
15 Traveller Accommodation Units
Advertised 30/05/2024. Tender preparation
Advertised 14/12/2023. Tender advertised October 2024
Advertised 14/12/2023. Tender advertised November 2024
Advertised 21/12/2023. Section 183 approved at Council Meeting October 2024
Advertised 04/04/2024. Tender advertised September 2024
Subject to Judicial Review
Detailed design ongoing – boundary agreement outstanding
Detailed design complete – to be advertised

## Slide 6
Approved Housing Bodies – Part V Delivery
LEA | Project | Units | Status
Clondalkin | Parklands, Citywest – Tuath Housing | 52 | Complete – delivered October 2024
 | Parsons Court, Newcastle. Co-operative Housing Ireland | 8 | On-site – completion Q4.2024
 | Seven Mills, Clondalkin Respond Housing | 172 | On-site – completion Q4.2024
 | Graydon, Newcastle Tuath Housing | 24 | On-site – phased delivery in Q4.2024 & Q2.2025
 | Gordon Park, Clondalkin Part V | 11 | On-site – delivery 2025
Parklands, Citywest
Seven Mills, Clondalkin

## Slide 7: Overview
Notes: Total Number of EOIs
No alt text provided
Number of EOIs by LEA
No alt text provided
Number of EOIs By Status
No alt text provided
image
No alt text provided
textbox
No alt text provided