## Slide 1
Social Housing Delivery
Tallaght Area Committee Meeting
25th November 2024

## Slide 3
Large Development Sites
Killinarden Foothills: 620 homes (including 125 social , 123 Private & 372 affordable purchase)
Pre-construction enabling and planning compliances works have commenced on site. Commencement notice expected to be lodged in November 2024. Phased delivery with first homes expected mid 2026.
Belgard Square North: 133 cost rental apartments
Contractor commenced on site April 2023. Delivery Q1 2025
Belgard Square North
Killinarden Foothills

## Slide 4
Own Build Developments
LEA | Project | Units | Status
Tallaght South | Rossfield Avenue | 16 | Tender currently advertised. Due to close this week.
Tallaght Central | St Aonghus Green (Age-Friendly) | 12 | Construction ongoing
3D image – St Aongus Green
3D Image – St Aongus Green

## Slide 5
Planning Derogation Sites – Section 179A / 161
Rossfield Avenue, Tallaght
16 Social Homes
Advertised 14/12/2023. Tender advertised October 2024
Deansrath & Melrose, Clondalkin
27 Age-Friendly Social Homes
Advertised 14/12/2023. Tender advertised November 2024
Kilcarbery Grange, Clondalkin
88 Social and Affordable Homes
Advertised 21/12/2023. Section 183 approved at Council Meeting October 2024
Alpine Heights, Clondalkin
13 Age-Friendly Social Homes
Advertised 04/04/2024. Tender advertised Sept 2024
Sarsfield Park, Lucan
5 Age-Friendly Social Homes
Advertised 11/04/2024. Tender advertised 28/08/2024
Castlefield, Old Knocklyon Road
33 Social and Affordable Homes
Subject to Judicial Review
Old Castle, Clondalkin
130 Social, Affordable and Traveller Accommodation Units
Detailed design ongoing – boundary agreement outstanding
Stocking Lane, Rathfarnham
25 Social Homes
Detailed design complete – to be advertised.
Owendoher Haven, Rathfarnham
9 Traveller Accommodation Units
FRA Ongoing
Kishogue Park, Clonburris
15 Traveller Accommodation Units
Advertised 30/05/2024. Tender preparation

## Slide 6
Approved Housing Bodies – Part V Delivery
LEA | Project | Units | Status
Tallaght South | Cuil Duin, Citywest Tuath Housing | 36 | All units delivered June 2024
 | Foxwood Barn, Citywest Tuath Housing | 108 | On site. Phased delivery from November 2024 to Q4.2025
 | Carrigmore Woods, Citywest. Tuath Housing | 137 | On-site – phased delivery from Q3.2025
Tallaght Central | Airton Plaza, Belgard Road Cluid Housing | 98 | On site. Due for delivery November 2024.
 | Airton Rise, Greenhills Road. Respond Housing | 213 | On-site – phased delivery from Q3.2025
 | Carrigmore View, Tallaght Dublin Simon | 4 | On-site – delivery Q1 2025
Airton Plaza, Belgard Road
Foxwood Barn, Citywest

## Slide 7: Overview
Notes: Total Number of EOIs
No alt text provided
Number of EOIs by LEA
No alt text provided
Number of EOIs By Status
No alt text provided
image
No alt text provided
textbox
No alt text provided