## Slide 1
Social Housing Delivery
Tallaght Area Committee Meeting 26th May 2025

## Slide 2: 2025
Notes: textbox
No alt text provided
Potential Units
No alt text provided
image
No alt text provided
Housing for All Delivery Pipeline 2025
No alt text provided
No. of Potential Units Per LEA
No alt text provided

## Slide 3
Large Development Sites
Killinarden Foothills: 620 homes (including 125 social , 123 Private & 372 affordable purchase)
Agreement has recently been reached with joint venture partners to progress the construction stage of these homes. Delivery of the first homes in phase 1 is anticipated for Q4.2025
.
Belgard Square North: 133 cost rental apartments
Substantial completion of units achieved in January 2025. Final snagging underway prior to handover. Advertising and tenanting of these homes to commence in June 2025.
Innovation Square,
Belgard Square North
Innovation Square,
Belgard Square North

## Slide 4
Own Build Developments
LEA | Project | Units | Status
Tallaght South | Rossfield | 16 | Contractor appointed. Awaiting start date.
Tallaght Central | St Aongus Green (Age-Friendly) | 12 | Construction commenced August 2024 – 50 week programme
St Aongus Green

## Slide 5
Approved Housing Bodies – Social Housing Investment Programme
LEA | Project | Units | Status
Tallaght South | Foxwood Barn, Citywest Tuath Housing | 39 | On-site – due to deliver Q4.2025
 | Carrigmore Woods, Citywest. Tuath Housing | 137 | On-site – phased delivery from Q3.2025
Tallaght Central | Airton Rise, Greenhills Road. Respond Housing | 213 | On-site – phased delivery from Q3.2025
Foxwood Barn,
Citywest
Airton Plaza
Airton Rise, Greenhills Road

## Slide 6: Overview
Notes: Total Number of EOIs
No alt text provided
Number of EOIs by LEA
No alt text provided
Number of EOIs By Status
No alt text provided
image
No alt text provided
textbox
No alt text provided