## Slide 1
Social Housing Delivery
Lucan Palmerstown North Clondalkin Area Committee Meeting
27th May 2025

## Slide 2: 2025
Notes: textbox
No alt text provided
Potential Units
No alt text provided
image
No alt text provided
Housing for All Delivery Pipeline 2025
No alt text provided
No. of Potential Units Per LEA
No alt text provided

## Slide 3
Large Development Sites
Kilcarbery Grange: 1,034 homes with 30% social (310 homes)
Phases 1, 2 and 3 of this project are now complete, with delivery of 273 social homes to date. Construction on phase 4 well advanced and will complete in mid 2025.
Clonburris: Phases 1 & 2 comprising 382 homes (149 social), Phases 3,4,5 with potential for 1,430* homes
Construction of Phase 2 – Canal Extension is well advanced and remains on track for completion by November 2025. The tender process for Phase 1 – Kishogue, involving the construction of 266 social, affordable, and cost rental homes, closed on 22 November 2024. The tender assessment has been completed, and the contract award is imminent. On-site works are expected to begin in Q2 2025. Following a presentation to the Council in November 2024, plans for approximately 1,275 social and affordable homes across Phases 3, 4, and 5 will shortly be submitted to An Bord Pleanála under a Part 10 planning application. A briefing session on the application will be arranged. Preparations are also underway to begin the procurement process for Phase 6 – Kishogue District Centre, with a targeted start date in early 2026.
Kilcarbery Grange
Clonburris Phase 1

## Slide 4
Own Build Developments
LEA | Project | Units | Status
Palmerstown- Fonthill | St Ronan’s Crescent (Age-Friendly) | 9 | Contractor appointed. Awaiting start date.
Lucan | Sarsfield Park (Age-Friendly) | 5 | Contractor on site.
St Ronan's Crescent Age Friendly Scheme
Omer Walk, Balgaddy

## Slide 5
Approved Housing Bodies – Social Housing Investment Programme
LEA |  | Units | Status
Lucan | Aderrig Heights Adamstown Fold | 14 | On site. Delivery from Q2.2025. Part V negotiations complete
 | Tandy’s Lane – 2 Oaklee | 14 | On site. Delivery from Q2.2025. Part V negotiations complete
 | Adamstown District Centre Tuath Housing | 44 | On-site – completion Q4.2025. Part V negotiations complete
 | St Helen’s Plaza, Adamstown Tuath Housing | 80 | On-site – phased delivery from Q1.2026
 | Somerton, Adamstown Cluid Housing | 68 | On-site – phased delivery from Q1.2026 Age Friendly Development
 | The Boulevard, Adamstown Part V | 19 | On site. Delivery from Q2.2026. Part V negotiations ongoing.
 | Aderrig, Phase 4 Part V | 36 | On site. Delivery from Q4.2026. Part V negotiations ongoing
Aderrig, Phase 3
Adamstown District Centre

## Slide 6: Overview
Notes: Total Number of EOIs
No alt text provided
Number of EOIs by LEA
No alt text provided
Number of EOIs By Status
No alt text provided
image
No alt text provided
textbox
No alt text provided