## Slide 1: Housing Delivery Report Clondalkin, Newcastle, Rathcoole, Saggart and Brittas ACM

## Slide 2: 2025
Notes: textbox
No alt text provided
Housing for All Delivery Pipeline 2025
No alt text provided
Potential Units
No alt text provided
image
No alt text provided
No. of Potential Units Per LEA
No alt text provided

## Slide 3: Large Development Sites
Kilcarbery Grange: 1,034 homes with 30% social (310 homes)
Phases 1, 2 and 3 of this project are now complete, with delivery of 288 social homes to date. Construction on phase 4 well advanced and will complete in late September 2025.
Clonburris Phases 1-6: Phases 1 & 2 comprising 382 homes (149 social), Phases 3,4,5 with potential for 1,275 homes & Phase 6 with potential for 650 homes
Phase 2 – Canal Extension is well advanced and remains on track for completion by November 2025.
Phase 1 – Kishoge. Cunninghams Contractors have been appointed to construct 284 social, affordable, cost rental & Traveller homes. Site clearance and decanting works are underway with formal construction commencing September 2025.
Phases 3, 4, 5 - plans for approximately 1,275 social and affordable homes have been submitted to An Coimisiún Pleanála under a Part 10 planning application. Submission period has ended with minimal submissions received. Decision expected by early 2026.
Phase 6 - Kishoge District Centre – approx. 650 homes, procurement process has commenced with contractor to be appointed by mid 2026.
Rathcoole: Approx 125 homes
Architect led design team have been appointed to progress the masterplan through to Part 10 planning application to An Bord Pleanála.

## Slide 4: SDCC Build Programme
LEA | Project | Units | Status
Clondalkin | Lindisfarne | 19 | Substantially complete December 2024
 | Canal Bank, Clonburris | 56 | On-site – delivery from November 2025. Mixed Tenure Scheme –56 Social homes & 60 Affordable Purchase homes.
 | Kilcarbery Grange | 47 | On-site – 288 delivered to date. Balance to be delivered by end September 2025
 | Alpine Heights (Age-Friendly) | 13 | Contractor on site. Delivery Q3.2026
 | Deansrath – Melrose | 27 | Contractor on site. Delivery Q3.2026
 | Kilcarbery School Site | 18 | Contractor on site. Delivery Q4.2025 / Q1.2026
Canal Bank, Clonburris

## Slide 5: AHB & Part V Delivery
LEA | Project | Expected Units | Status
Clondalkin | Parsons Court, Newcastle. CHI | 8 | Complete
 | Gordon Park, Part V - FOLD | 13 | On-site – Completion Q3.2025
 | Keepers Lock, Clonburris Part V - Oaklee | 86 | On-site – phased handover from November 2025. 26 Affordable Purchase agreed under PV
 | Garters Lane, Saggart Part V - Tuath | 23 | Part V negotiations complete. Phased handover through 2025 & 2026
 | Parkleigh Copse, Sevenmills Part V - Respond | 15 | Part V negotiations concluded. Completion Q4.2025
 | St Johns Road, Clondalkin Part V – CHI | 4 | Part V negotiations concluded. Completion Q4.2025
 | Main Street, Saggart Part V – Cluid | 3 | Part V negotiations concluded. Completion Q4.2025
 | Graydon, Newcastle Part V - Tuath | 8 | Part V negotiations concluded. Completion Q4.2025
 | Lockhouse Way, Sevenmills Part V - Cluid | 28 | Part V negotiations ongoing. Completion Q4.2025
 | Mill Road, Saggart Part V – Tuath | 26 | Part V negotiations concluded. Phased completion through 2025 & 2026

## Slide 6: Housing Acquisitions Programme 2025
Acquisitions complete to date
60
Sale Agreed
13
Acquisitions in Conveyance
14
Anticipated Completions for 2025
87
Chart: 
| Complete to date | In conveyance | Sale Agreed
 | 60 | 14 | 13

## Slide 7: Thank you