## Slide 1: Bus Stop Enhancement Programme Update
Department: Planning and Transport
Director: Eoin Burke

## Slide 2: Programme Overview:
Title: Bus Stop Enhancement Programme
Funded and overseen by the NTA
Delivered locally by SDCC Traffic Section (Civil Work)
Improves accessibility, safety, and comfort at bus stops
Supports BusConnects and Active Travel initiatives

## Slide 3: Key Objectives:
Title: Bus Stop Enhancement Programme
Provide safe, accessible, and user-friendly bus stops
Ensure universal access for all passengers
Prepare sites for bus shelters and RTPI displays
Standardise Bus Stop layouts across the country

## Slide 4: Shelter Selection (NTA Role)
Title: Bus Stop Enhancement Programme
NTA decides which bus stops receive shelters
Selection criteria include: Passenger demand and boarding numbers Accessibility and proximity to key trip generators (schools, healthcare, etc.) Safety and visibility at the bus stop Adequate space and footpath width

## Slide 5: Works Delivery
Title: Bus Stop Enhancement Programme
SDCC: delivers civil works
Types of Works: Footpath build-outs and kerb realignment
Hardstanding and drainage works
Tactile paving for accessibility
Ducting and sockets for future RTPI or shelters
Integration with existing pedestrian and cycle network
NTA: manages bus shelter installation via national contractor

## Slide 6: Delivery Process
Title: Bus Stop Enhancement Programme
Bus Stop upgrade identification and prioritisation
Design & Road Safety Audit (if required)
Funding allocation through NTA PRS system
Construction delivery

## Slide 7: Current Upgrade Works in progress
Title: Bus Stop Enhancement Programme
Bus Stop Enhancement Programme |  |  | 
 |  | BSEP | Working status
Approved by NTA |  | Location | GM link
Platecode | 2349 | Alderwood Old Blessington Road Tallaght | https://maps.app.goo.gl/y8tLUoECiHtbm7Yd7
 | 4606 | Foxborough Balgaddy Road Lucan | https://maps.app.goo.gl/NcgUfdwpcRAnYihX8
 | 4619 | Foxborough Balgaddy Road Lucan | https://maps.app.goo.gl/tKC9UZosAg6Pm9M89
Reviewed drawings to be revised |  |  | 
Platecode | 4532 | Hazelwood Cresent (1) Clondalkin | https://maps.app.goo.gl/yxP8S6jpTG8vZv739
 | 4534 | Parkview Lawns Clondalkin | https://maps.app.goo.gl/91kcyJusyVqqNyvh8
 | 2168 | St Johns Lawn Clondalkin | https://maps.app.goo.gl/P6punqYHwV7p3BbY6
 | 4644 | Fortunestown Way | https://maps.app.goo.gl/oGFxKjcjA7XftgXJ7
 | 2745 | Cookstown Road Tallaght | https://maps.app.goo.gl/i1zru1DuEabo4HdD9
 | 2748 | Maplewood Road Tallaght | https://maps.app.goo.gl/hGvceqMKvAUdVZFs8
Reviewed drawings not to procede |  |  | 
Platecode | 3420 | Cherrywood Villas Clondalkin | https://maps.app.goo.gl/VK9yRJBdtLXL24Pu7
 | 4536 | Hazelwood Cresent (2) Clondalkin | https://maps.app.goo.gl/qswVYCmMWP63ppkVA
In Design |  |  | 
Platecodes | 8338 | Backweston Park R403 Co Dublin | https://maps.app.goo.gl/4LmXabevBZU5gwRRA
 | 3896 | R403 (1) Tubber Lane | https://maps.app.goo.gl/PTBVksEMBQrfNpJPA
 | 3943 | R403 (2)Hallwell | https://maps.app.goo.gl/db1yMaoZjpx787fT7
 | 2160 | Convent Road Clondalkin | https://maps.app.goo.gl/yd1xpMSqZUwibG3V6
 | 2558 | Killinarden (1) Tallaght | https://maps.app.goo.gl/CNcr9uDnedqTFZm1A
 | 2571 | Killinarden (2) Tallaght | https://maps.app.goo.gl/ZtVvriZooN3hmRme7
 | 4886 | Woodstown Knocklyon | https://maps.app.goo.gl/rCzj2c6ipQD9Azrw7
 | 2518 | Knocklyn Ave Firhouse Road | https://maps.app.goo.gl/pigryh6zbKC7P5LN8
 | 2547 | Knocklyn Ave Firhouse Road | https://maps.app.goo.gl/aKCupaysjcFxvegQ6
 | 7803 | Balgaddy Road Lucan | https://maps.app.goo.gl/ZLCq5tCM769MiTHP8
 | 7386 | Foxborough Balgaddy Road Lucan | https://maps.app.goo.gl/wB3EiHD1DY7TgxHr7
 | 2570 | Killinarden Heights | https://maps.app.goo.gl/NVRAENw4gFXpGgsS7
 | 7550 | Killinarden Heights | https://maps.app.goo.gl/GjVuQEPtnMX47ME78
 | 2561 | Killinarden Heights | https://maps.app.goo.gl/Ca5Yp3rqr8EcNL3m8
 | 2568 | Killinarden Heights | https://maps.app.goo.gl/ekuqqDFfcKBvnUdC7
 | 2566 | Killinarden Heights | https://maps.app.goo.gl/qb6H2YuAtfgtnTFu5
 | 4001 | Leixlep Road | https://maps.app.goo.gl/dYnfE7H2J1zWaBCB8
 | 2559 | Killinarden Heighs | https://maps.app.goo.gl/FCu7fDTQ4R7dmEwa6
 | 4564 | Rathcoole | https://maps.app.goo.gl/1Tf1w4qgz9HqsXVY8
 | 2204 | Palmerstown Kennelsfort Road | https://maps.app.goo.gl/YttcezYWhaCjnZ8o6
Road safety Audit |  |  | 
The RSAs are required the platecodes below |  |  | 
Deadline for qoutes is 4th July | 2349 | Alderwood Old Blessington Road Tallaght | https://maps.app.goo.gl/y8tLUoECiHtbm7Yd7
 | 4606 | Foxborough Balgaddy Road Lucan | https://maps.app.goo.gl/NcgUfdwpcRAnYihX8
 | 4619 | Foxborough Balgaddy Road Lucan | https://maps.app.goo.gl/tKC9UZosAg6Pm9M89
Priority Bus Shelters (damaged replacement needed) |  |  | 
 | 3368 | Finnstown Abbey | https://maps.app.goo.gl/1RWi54wk1gN5mECH6
 | 2755 | Cookstown Est Rd | https://maps.app.goo.gl/ymgZ9sZAm6zXAtXS8
The table is for illustrative purposes only to demonstrate our list of candidate schemes. All sites are subject to NTA final approval.
Draft

## Slide 8: Next Steps
Title: Bus Stop Enhancement Programme
Deliver 2025 BSEP schemes
Prepare 2026 programme with expanded accessibility focus
Increase collaboration with NTA on shelter rollout
Continued Councillor and community engagement on upgrade works prioritisation

## Slide 9: Thank you !
Multi-annual bus stop enhancement programme in place
Candidate upgrade sites suggested by the public, Councillors, SDCC and NTA
Priority schemes agreed and funded by NTA
Joint responsibility between SDCC and NTA to deliver the upgrades
Summary
Title: Bus Stop Enhancement Programme