## Slide 1: Housing Delivery Report Rathfarnham Templeogue Firhouse Bohernabreena ACM

## Slide 2: 2025
Notes: Housing for All Delivery Pipeline 2025
No alt text provided
No. of Potential Units Per LEA
No alt text provided
textbox
No alt text provided
Potential Units
No alt text provided
image
No alt text provided

## Slide 3: SDCC Build Programme
LEA | Project | Units | Status
Firhouse – Bohernabreena | Homeville – Watercourse Grove | 16 | Complete July 2025 – Fully Allocated
 | Pearse Brothers Park | 10 | Construction ongoing. 15 month programme. Age-Friendly Development
 | Stocking Avenue | 25 | Part 8 approved October 2025 – Progress to detailed design and procurement
Stocking Avenue
Pearse Brothers Park

## Slide 4: AHB & Part V Delivery
LEA | Project | Expected Units | Status
Rathfarnham – Templeogue | Grange Road, Rathfarnham Part V & AHB Acquisition – Oaklee | 37 | 37 units complete. EDD November 2025 – Allocations process has commenced
 | Walkinstown House Part V & AHB Acquisition – Cluid | 66 | Complete October 2025. Allocations process commenced.
 | Stone Park Hall, Nutgrove Avenue Part V & AHB Acquisition – Oaklee | 28 | On-site. EDD December 2025
 | Watsons Place, Ballyroan Part V | 2 | On-site. EDD December 2025
 | Whitehall Road West AHB Build - Focus Ireland | 13 | On-site. Delivery from Q1.2026. Age Friendly Development
Firhouse – Bohernabreena | Oldcourt Park, Dodderbrook Part V | 2 | On-site. EDD November 2025. Part V negotiations complete
 | St Winnows, Stocking Lane Part V | 25 | On site. Due for delivery Q3 2026. Part V negotiations ongoing.
 | Firhouse Inn Part V | 15 | On site. Due for delivery Q4 2026. Part V negotiations ongoing.

## Slide 5: Housing Acquisitions Programme 2025
Acquisitions complete to date
72
Sale Agreed / Negotiation
23
Acquisitions in Conveyance
11
Anticipated Completions for 2025
83
Chart: 
| Complete to date | In conveyance | Sale Agreed / Negotiation
 | 72 | 11 | 23

## Slide 6: Thank you