## Slide 1: Update on Public Lighting at Rathfarnham/Templeogue/Firhouse/Bohernabreena RTFB Area Committee Meeting - January 2026
Created by C. Lambert
Presented by C.Lambert

## Slide 2: Status of Outstanding Repairs
As of end of December 2025, the status is as follows:
This gives a total of 255 faults at present, which represents 2.5% of the overall lighting stock in the RTFB area.
Standard Outages | 196
Cable Fault or ESB Attendance Required | 33
Access issues – e.g. tree prune or traffic management required. | 26

## Slide 3: The repair approach is as follows:
Since most of these outages are the old obsolete low pressure sodium ‘orange’ lights, our contractor cannot honour the standard two-week repair time.
This is because the poles are supplied directly from ESBN supply pillars. We are not permitted to replace the whole fitting without ESBN site attendance. We can only replace the lamp.
The lamp replacements are in extremely short supply and are only available to be sourced/harvested from our ongoing ESBN/SDCC LED Upgrade Programme.

## Slide 4
There are 196 of this type of outage in the area. We address them on a ‘first reported/first repaired’ basis but the main delay is due to a lack of parts.
The other 59 outages are more complex. Cable fault repairs require a road opening licence, civil works and an agreed traffic management plan, which all take time and resources to progress. In addition, because of the age profile of these poles/cables, most reconnections post repair will require site attendance by ESBN, which can add a huge delay to the full completion of the repair.
The most efficient remedy is to eliminate these old fittings altogether via our ESBN/LED Upgrade Programme.
This programme is a planned process that is a joint project with ESBN.

## Slide 5
We have project meetings every month with ESBN senior management and site staff to expedite this process as much as possible.
The main stumbling block is a resource issue with ESBN themselves. They cooperate as best as they can and are working very well with us on site. But every time there is a severe weather event, it slows down even the agreed monthly site works dates.
This year however, we have been promised a considerable increase in resources from them via the forthcoming availability of approved 3rd party subcontractors.

## Slide 6: Planned Upgrades for 2026 in your Area
426 | Rathfarnham Templeogue
308 | Firhouse Bohernabreena
734 | Total

## Slide 7: Planned Upgrades for 2026 in your Area
Corrig Close | Rathfarnham Templeogue
Glendoo Close | Rathfarnham Templeogue
Keadeen Avenue | Rathfarnham Templeogue
Kilakee Close | Rathfarnham Templeogue
Kilakee Drive | Rathfarnham Templeogue
Kilmashogue Close | Rathfarnham Templeogue
Kilmashogue Drive | Rathfarnham Templeogue
Kilmashogue Grove | Rathfarnham Templeogue
Kippure Avenue | Rathfarnham Templeogue
Limekiln Green | Rathfarnham Templeogue
Lugnaquilla Avenue | Rathfarnham Templeogue
Three Rock Close | Rathfarnham Templeogue
Tibradden Close | Rathfarnham Templeogue
Tibradden Drive | Rathfarnham Templeogue
Tibradden Grove | Rathfarnham Templeogue
Tonduff Close | Rathfarnham Templeogue

## Slide 8: Planned Upgrades for 2026 in your Area - continued
Cypress Drive | Rathfarnham Templeogue
Cypress Grove South | Rathfarnham Templeogue
Domville Drive | Rathfarnham Templeogue
Domville Green | Rathfarnham Templeogue
Domville Road | Rathfarnham Templeogue
Glendown Road | Rathfarnham Templeogue
Orwell Park Avenue | Rathfarnham Templeogue
Orwell Park Close | Rathfarnham Templeogue
Orwell Park Crescent | Rathfarnham Templeogue
Orwell Park Dale | Rathfarnham Templeogue
Orwell Park Drive | Rathfarnham Templeogue
Orwell Park Glade | Rathfarnham Templeogue
Orwell Park Glen | Rathfarnham Templeogue
Orwell Park Green | Rathfarnham Templeogue
Orwell Park Grove | Rathfarnham Templeogue
Orwell Park Heights | Rathfarnham Templeogue

## Slide 9: Planned Upgrades for 2026 in your Area - continued
Orwell Park Lawns | Rathfarnham Templeogue
Orwell Park Rise | Rathfarnham Templeogue
Orwell Park View | Rathfarnham Templeogue
Orwell Park Way | Rathfarnham Templeogue
Orwell Park-The Manor | Rathfarnham Templeogue
Orwell Road | Rathfarnham Templeogue
Osprey Drive | Rathfarnham Templeogue
Rossmore Avenue | Rathfarnham Templeogue
Rossmore Close | Rathfarnham Templeogue
Rossmore Crescent | Rathfarnham Templeogue
Rossmore Drive | Rathfarnham Templeogue
Rossmore Grove | Rathfarnham Templeogue
Rossmore Lawns | Rathfarnham Templeogue
Rossmore Park | Rathfarnham Templeogue
Rossmore Road | Rathfarnham Templeogue
Templeogue Wood | Rathfarnham Templeogue
The Watercourse | Rathfarnham Templeogue

## Slide 10: Planned Upgrades for 2026 in your Area - continued
Willington Avenue | Rathfarnham Templeogue
Willington Court | Rathfarnham Templeogue
Willington Crescent | Rathfarnham Templeogue
Willington Drive | Rathfarnham Templeogue
Willington Grove | Rathfarnham Templeogue
Willington Lawn | Rathfarnham Templeogue
Willington Park | Rathfarnham Templeogue

## Slide 11: Planned Upgrades for 2026 in your Area - continued
Edmondstown Green | Firhouse Bohernabreena
Edwards Court | Firhouse Bohernabreena
Glenmore Court | Firhouse Bohernabreena
Glenmore Green | Firhouse Bohernabreena
Glenmore Park | Firhouse Bohernabreena
Moyville | Firhouse Bohernabreena

## Slide 12: Planned Upgrades for 2026 in your Area - continued
Allenton Avenue | Firhouse Bohernabreena
Allenton Crescent | Firhouse Bohernabreena
Allenton Drive | Firhouse Bohernabreena
Allenton Gardens | Firhouse Bohernabreena
Allenton Green | Firhouse Bohernabreena
Allenton Lawns | Firhouse Bohernabreena
Allenton Park | Firhouse Bohernabreena
Allenton Road | Firhouse Bohernabreena
Allenton Way | Firhouse Bohernabreena
Glencarrig Court | Firhouse Bohernabreena
Glencarrig Drive | Firhouse Bohernabreena
Glencarrig Green | Firhouse Bohernabreena
Oldcourt Lawn | Firhouse Bohernabreena
Oldcourt Road | Firhouse Bohernabreena

## Slide 13: Planned Upgrades for 2026 in your Area - continued
Ballycullen Way | Firhouse Bohernabreena
Carriglea Avenue | Firhouse Bohernabreena
Carriglea Court | Firhouse Bohernabreena
Carriglea Downs | Firhouse Bohernabreena
Carriglea Drive | Firhouse Bohernabreena
Carriglea Grove | Firhouse Bohernabreena
Carriglea Rise | Firhouse Bohernabreena
Carriglea View | Firhouse Bohernabreena
Carriglea Walk | Firhouse Bohernabreena
Carrigwood/Carriglea Green | Firhouse Bohernabreena
Killakee Avenue | Firhouse Bohernabreena
Killakee Court | Firhouse Bohernabreena
Killakee Gardens | Firhouse Bohernabreena
Killakee Green | Firhouse Bohernabreena
Killakee Grove | Firhouse Bohernabreena
Killakee Lawns | Firhouse Bohernabreena

## Slide 14: Planned Upgrades for 2026 in your Area - continued
Killakee Park | Firhouse Bohernabreena
Killakee Rise | Firhouse Bohernabreena
Killakee View | Firhouse Bohernabreena
Killakee Walk | Firhouse Bohernabreena
Killakee Way | Firhouse Bohernabreena

## Slide 15
The successful completion of this plan is entirely dependent on resources throughout the year.
Any of the listed estates that are not addressed in 2026 will be prioritised for 2027.
When this list is completed, there will be 876 upgrades remaining to be carried out in order to close out the programme in your area.

## Slide 16: Thank you