COMHAIRLE CHONTAE ÁTHA CLIATH THEAS

SOUTH DUBLIN COUNTY COUNCIL

# MEETING OF TALLAGHT AREA COMMITTEE (1)

18th September 2006

H I – (8)

## Report on Housing Construction Programme:

The up-to-date position of the construction programme for the County area is set out in the detail below: -

Completions in 2004:-

| Total | No. of Units | 81 |
| --- | --- | --- |

Completions in 2005:-

| Scheme Name | No. of Units | Completion Dates |
| --- | --- | --- |
| Russell Square | 110 | 2005 |
| Bawnlea | 7 | March 2005 |
| Jobstown Village Core | 10 | March 2005 |
| Cushlawn, Phase II | 31 | 2005 |
| Daletree, Ballycragh | 8 | September 2005 |
| Fettercairn Village | 22 | 2005 |
| Sub Total | 188 |  |

Completions in 2006:-

| Total | No. of Units | Completion Dates |
| --- | --- | --- |
| Fettercairn Village | 9 | February 2006 |
| Fettercairn Village | 9 | May 2006 |
| Deerpark (Joint Venture) | 11 | May 2006 |
| Deerpark (Joint Venture) | 14 | August 2006 |
| Sub Total | 43 |  |

### On Site:-

| Scheme Name | No. of Units on Site | Completion Dates |
| --- | --- | --- |
| Avonbeg, Phase 3 | 47 | In phases end September, Early October 2006 |
| Fettercairn VII & Community Facility | 2 | October 2006 |
| Fortunestown B, Phase 2 | 66 (+52 Vol. Units) | In phases from October 2006 |
| Fortunestown B, Phase 4 | 120 | In phases from October 2006 |
| Fortunestown B, Phase 1 | 110 | In phases from December 2006 |
| Deerpark (Joint Venture) | 94 | (In phases) May 2006 |
| Daletree (Part 5/Joint Venture) | 27 | (in phases) October 2005 |
| Hunterswood (Part V) | 9 | Late 2006 |
| Brookfield Village+ Community Facility | 16 | Late September 2006 |
| Deerpark (Part V) | 36 | From May 2006 (in phases) |
| Belfry (Part V) | 35 | December 2006 |
| Belgard Square (Part V) | 44 | Late 2006 |
| Castlepark | 9 | July 2007 |
| Cushlawn Phase 3 | 22 | December 2007 |
| Sub.Total | 637 |  |

Tenders Recommended

| Scheme Name | No of Units |
| --- | --- |
| Kilcarrig Phase 3 (SH274) | Tender approval in the sum of €13,694,694 received from the DoEHLG for approval for the construction of 80 units by D&I Construction Ltd., Tyrell House, Main Street Blessington, Co Wicklow |
| Sub Total | 80 |

Tender Production

| Scheme Name | No. of Housing Units |
| --- | --- |
| Kiltalown Green | 28 |
| Sub Total | 28 |

Part 8 Approved by Council:-

| Scheme Name | No. of Housing Units |
| --- | --- |
| Avonbeg Phase 4 (SH252) | 7 & St Muirins House – Cost Plan approved by DOEHLG on 11/7/2006. Brief being prepared for design team for the community facility with a view to inviting tenders late November/early December 2006 |
| ### Fortunestown B, Phase 3 & 5 | 160 - Part 8 approved for 160 affordable units in the first instance. Draft procurement Plan for Affordable housing by 8/9/2006 |
| ### Fettercairn Phase 2 | ### 33 – Part 8 Report approved by Council in July 2006. Cost plan submitted to DOELG on 10/8/2006 |
| ### Knockmore House (incl. 15 units for Bernardos) | ### 89 – meeting to be arranged with unit design team. Cost plan target date October 2006 |
| ### Rossfield Infill | 9 plus commercial units – Part 8 approved at July 2006 meeting – further consultation required. Cost Plan target date 18/8/06 |
| ### Castletymon | 42 – Part 8 approved at July 2006 for 42 units. Plans amended to address residents concerns. Further public consultation took place with residents on 27th July 2006. Cost plan being prepared following consultation. |
| ### Total | 335 |

At Concept/Design Stage:-

| ### Scheme Name | ### Approx . No. Of Units |
| --- | --- |
| ### Kilclare, Phase2 | ### 30 (concepts presented to Tallaght Area Committee Meeting 16/06//2003) |
| ### Kilclare Phase3 | ### 15 units |
| Whitestown Stream | 147 private/affordable/social/ voluntary units |
| Suncroft | 10 units |
| Whitebrook Park | 25 units - (concepts presented to Tallaght Area Committee Meeting 20/09/2004) – land transfer to be finalised by development department |
| ### Stocking Lane | - (concept under preparation) |
| ### Swiftbrook | 11 units -(concept presented to Tallaght Area Committee Meeting 08/12/04) |
| ### Sub Total | 228 |

Other potential sites are also being examined.