COMHAIRLE CHONTAE ÁTHA CLIATH THEAS

SOUTH DUBLIN COUNTY COUNCIL

# MEETING OF TALLAGHT AREA COMMITTEE (1)

16th October 2006

H I – 14

## Report on Housing Construction Programme:

The up-to-date position of the construction programme for the County area is set out in the detail below: -

Completions in 2004:-

| Total | No. of Units | 81 |
| --- | --- | --- |

Completions in 2005:-

| Scheme Name | No. of Units | Completion Dates |
| --- | --- | --- |
| Russell Square | 110 | 2005 |
| Bawnlea | 7 | March 2005 |
| Jobstown Village Core | 10 | March 2005 |
| Cushlawn, Phase II | 31 | 2005 |
| Daletree, Ballycragh | 8 | September 2005 |
| Fettercairn Village | 22 | 2005 |
| Sub Total | 188 |  |

Completions in 2006:-

| Total | No. of Units | Completion Dates |
| --- | --- | --- |
| Fettercairn Village | 9 | February 2006 |
| Fettercairn Village | 9 | May 2006 |
| Deerpark (Joint Venture) | 11 | May 2006 |
| Deerpark (Joint Venture) | 14 | August 2006 |
| Deerpark (Joint Venture) | 16 | September 2006 |
| Sub Total | 59 |  |

### On Site:-

| Scheme Name | No. of Units on Site | Completion Dates |
| --- | --- | --- |
| Avonbeg, Phase 3 | 47 | Late October 2006 |
| Fettercairn PH2 & Community Facility | 2 | October 2006 |
| Fortunestown B, Phase 2 | 66 (+52 Vol. Units) | In phases from October 2006 |
| Fortunestown B, Phase 4 | 120 | In phases from October 2006 |
| Fortunestown B, Phase 1 | 110 | In phases from December 2006 |
| Deerpark (Joint Venture) | 78 | (In phases) May 2006 |
| Daletree (Part 5/Joint Venture) | 27 | (in phases) October 2005 |
| Hunterswood (Part V) | 9 | Late 2006 |
| Brookfield Village+ Community Facility | 16 | Late October 2006 |
| Deerpark (Part V) | 36 | From May 2006 (in phases) |
| Belfry (Part V) | 35 | December 2006 |
| Belgard Square (Part V) | 44 | Late 2006 |
| Castlepark | 9 | July 2007 |
| Cushlawn Phase 3 | 22 | December 2007 |
| Sub.Total | 621 |  |

Tenders Recommended

| Scheme Name | No of Units |
| --- | --- |
| Kilcarrig Phase 3 (SH274) | Tender approval in the sum of €13,694,694 received from the DoEHLG for approval for the construction of 80 units by D&I Construction Ltd., Tyrell House, Main Street Blessington, Co Wicklow |
| Sub Total | 80 |

Tender Production

| Scheme Name | No. of Housing Units |
| --- | --- |
| Kiltalown Green | 28 |
| Sub Total | 28 |

Part 8 Approved by Council:-

| Scheme Name | No. of Housing Units |
| --- | --- |
| Avonbeg Phase 4 (SH252) | 7 & St Muirins House – Cost Plan approved by DOEHLG on 11/7/2006. Brief being prepared for design team for the community facility with a view to inviting tenders late November/early December 2006 |
| ### Fortunestown B, Phase 3 & 5 | 160 - Part 8 approved for 160 affordable units in the first instance. Draft procurement Plan for Affordable housing being finalised |
| ### Fettercairn Phase 2 | ### 33 – Part 8 Report approved by Council in July 2006. Cost plan submitted to DOELG on 23/08/06.DOELG queries to be dealt with for approval by Nov 06 .Tender target date 2nd quarter 2007 |
| ### Knockmore House (incl. 15 units for Bernardos) | ### 89 – Cost plan target date October 2006 |
| ### Rossfield Infill | 9 plus commercial units – Part 8 approved at July 2006 meeting – further consultation required. Submitted to DOE for approval 4/9/06 |
| ### Castletymon | 42 – Part 8 approved at July 2006 for 42 units. Plans amended to address residents concerns. Further public consultation took place with residents on 27th July 2006. Cost plan being prepared following consultation. Further meeting to be held with Local Residents and 5 Local Councillors |
| ### Total | 335 |

At Concept/Design Stage:-

| ### Scheme Name | ### Approx . No. Of Units |
| --- | --- |
| ### Kilclare, Phase2 | ### 30 (concepts presented to Tallaght Area Committee Meeting 16/06//2003) |
| ### Kilclare Phase3 | ### 15 units |
| Whitestown Stream | 147 private/affordable/social/ voluntary units |
| Suncroft | 10 units |
| Whitebrook Park | 25 units - (concepts presented to Tallaght Area Committee Meeting 20/09/2004) – land transfer to be finalised by development department |
| ### Stocking Lane | - (concept under preparation) |
| ### Swiftbrook | 11 units -(concept presented to Tallaght Area Committee Meeting 08/12/04) |
| ### Sub Total | 228 |

Other potential sites are also being examined.